## Summary Sheet
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SUMMARY SHEET
TENDERER'S NAME | Countryside Partnerships
SUMMARY OF TOTAL COMBINED COST FOR TIMBER FRAME AND TRADITIONAL CONSTRUCTION
LOT | COMBINED TOTAL
Low Value L1 | 458350
Low Value L2 | 458350
Low Value L3 | 458350
Low Value L4 | 458350
Low Value L5 | 458350
High Value H1 | 20721039.2831
High Value H2 | 19847640.2882
NOTE: Where the 'Combined Total' cells above are highlighted red it is taken that the contractor is not tendering for the lot in question. Only pricing in the green highlighted cells will be taken forward.

## Low val Lot 1
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L1
TRADITIONAL CONSTRUCTION
LOCATION | Greater Manchester and Merseyside, Cheshire, Derbyshire West and Staffordshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks |  | 0
Contracts Manager | 68 | weeks |  | 0
Site Engineer | 68 | weeks |  | 0
Site Manager | 68 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 68 | weeks |  | 0
Labourer (including at handover) | 68 | weeks |  | 0
Quantity Surveying / Commercial Management | 68 | weeks |  | 0
Planner | 68 | weeks |  | 0
Health & Safety Officer | 68 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 68 | weeks |  | 0
Meeting room (inc furniture) | 68 | weeks |  | 0
Canteens and Kitchens | 68 | weeks |  | 0
Drying room | 68 | weeks |  | 0
Toilets and washrooms | 68 | weeks |  | 0
Secure stores | 68 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 68 | weeks |  | 0
IT systems with email and internet capability | 68 | weeks |  | 0
Consumables and services associated with site accommodation | 68 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 68 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks |  | 0
Gas Supply | 68 | weeks |  | 0
Electric supply, Lighting and power | 68 | weeks |  | 0
Drainage | 68 | weeks |  | 0
Security
Night watchman | 68 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 68 | weeks |  | 0
Material distribution
Forklift and driver | 34 | weeks |  | 0
Site plant
Small Dumper | 34 | weeks |  | 0
Mixer | 34 | weeks |  | 0
Road Sweeper including driver and fuel | 34 | weeks |  | 0
Excavator / mini digger including driver and fuel | 34 | weeks |  | 0
Small tools and equiptment | 34 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %)
Profit (expressed as a %)
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L1
TIMBER FRAME CONSTRUCTION
LOCATION | Greater Manchester and Merseyside, Cheshire, Derbyshire West and Staffordshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks |  | 0
Contracts Manager | 52 | weeks |  | 0
Site Engineer | 52 | weeks |  | 0
Site Manager | 52 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 52 | weeks |  | 0
Labourer (including at handover) | 52 | weeks |  | 0
Quantity Surveying /Commercial Management | 52 | weeks |  | 0
Planner | 52 | weeks |  | 0
Health & Safety Officer | 52 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 52 | weeks |  | 0
Meeting room (inc furniture) | 52 | weeks |  | 0
Canteens and Kitchens | 52 | weeks |  | 0
Drying room | 52 | weeks |  | 0
Toilets and washrooms | 52 | weeks |  | 0
Secure stores | 52 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 52 | weeks |  | 0
IT systems with email and internet capability | 52 | weeks |  | 0
Consumables and services associated with site accommodation | 52 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 52 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks |  | 0
Gas Supply | 52 | weeks |  | 0
Electric supply, Lighting and power | 52 | weeks |  | 0
Drainage | 52 | weeks |  | 0
Security
Night watchman | 52 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 52 | weeks |  | 0
Material distribution
Forklift and driver | 26 | weeks |  | 0
Site plant
Small Dumper | 26 | weeks |  | 0
Mixer | 26 | weeks |  | 0
Road Sweeper including driver and fuel | 26 | weeks |  | 0
Excavator / mini digger including driver and fuel | 26 | weeks |  | 0
Small tools and equiptment | 26 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OHP | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 458350

## Low val Lot 2
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L2
TRADITIONAL CONSTRUCTION
LOCATION | Lancashire and Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks |  | 0
Contracts Manager | 68 | weeks |  | 0
Site Engineer | 68 | weeks |  | 0
Site Manager | 68 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 68 | weeks |  | 0
Labourer (including at handover) | 68 | weeks |  | 0
Quantity Surveying / Commercial Management | 68 | weeks |  | 0
Planner | 68 | weeks |  | 0
Health & Safety Officer | 68 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 68 | weeks |  | 0
Meeting room (inc furniture) | 68 | weeks |  | 0
Canteens and Kitchens | 68 | weeks |  | 0
Drying room | 68 | weeks |  | 0
Toilets and washrooms | 68 | weeks |  | 0
Secure stores | 68 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 68 | weeks |  | 0
IT systems with email and internet capability | 68 | weeks |  | 0
Consumables and services associated with site accommodation | 68 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 68 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks |  | 0
Gas Supply | 68 | weeks |  | 0
Electric supply, Lighting and power | 68 | weeks |  | 0
Drainage | 68 | weeks |  | 0
Security
Night watchman | 68 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 68 | weeks |  | 0
Material distribution
Forklift and driver | 34 | weeks |  | 0
Site plant
Small Dumper | 34 | weeks |  | 0
Mixer | 34 | weeks |  | 0
Road Sweeper including driver and fuel | 34 | weeks |  | 0
Excavator / mini digger including driver and fuel | 34 | weeks |  | 0
Small tools and equiptment | 34 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L2
TIMBER FRAME CONSTRUCTION
LOCATION | Lancashire and Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks |  | 0
Contracts Manager | 52 | weeks |  | 0
Site Engineer | 52 | weeks |  | 0
Site Manager | 52 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 52 | weeks |  | 0
Labourer (including at handover) | 52 | weeks |  | 0
Quantity Surveying /Commercial Management | 52 | weeks |  | 0
Planner | 52 | weeks |  | 0
Health & Safety Officer | 52 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 52 | weeks |  | 0
Meeting room (inc furniture) | 52 | weeks |  | 0
Canteens and Kitchens | 52 | weeks |  | 0
Drying room | 52 | weeks |  | 0
Toilets and washrooms | 52 | weeks |  | 0
Secure stores | 52 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 52 | weeks |  | 0
IT systems with email and internet capability | 52 | weeks |  | 0
Consumables and services associated with site accommodation | 52 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 52 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks |  | 0
Gas Supply | 52 | weeks |  | 0
Electric supply, Lighting and power | 52 | weeks |  | 0
Drainage | 52 | weeks |  | 0
Security
Night watchman | 52 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 52 | weeks |  | 0
Material distribution
Forklift and driver | 26 | weeks |  | 0
Site plant
Small Dumper | 26 | weeks |  | 0
Mixer | 26 | weeks |  | 0
Road Sweeper including driver and fuel | 26 | weeks |  | 0
Excavator / mini digger including driver and fuel | 26 | weeks |  | 0
Small tools and equiptment | 26 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OHP | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 458350

## Low val Lot 3
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L3
TRADITIONAL CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks |  | 0
Contracts Manager | 68 | weeks |  | 0
Site Engineer | 68 | weeks |  | 0
Site Manager | 68 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 68 | weeks |  | 0
Labourer (including at handover) | 68 | weeks |  | 0
Quantity Surveying / Commercial Management | 68 | weeks |  | 0
Planner | 68 | weeks |  | 0
Health & Safety Officer | 68 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 68 | weeks |  | 0
Meeting room (inc furniture) | 68 | weeks |  | 0
Canteens and Kitchens | 68 | weeks |  | 0
Drying room | 68 | weeks |  | 0
Toilets and washrooms | 68 | weeks |  | 0
Secure stores | 68 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 68 | weeks |  | 0
IT systems with email and internet capability | 68 | weeks |  | 0
Consumables and services associated with site accommodation | 68 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 68 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks |  | 0
Gas Supply | 68 | weeks |  | 0
Electric supply, Lighting and power | 68 | weeks |  | 0
Drainage | 68 | weeks |  | 0
Security
Night watchman | 68 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 68 | weeks |  | 0
Material distribution
Forklift and driver | 34 | weeks |  | 0
Site plant
Small Dumper | 34 | weeks |  | 0
Mixer | 34 | weeks |  | 0
Road Sweeper including driver and fuel | 34 | weeks |  | 0
Excavator / mini digger including driver and fuel | 34 | weeks |  | 0
Small tools and equiptment | 34 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L3
TIMBER FRAME CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks |  | 0
Contracts Manager | 52 | weeks |  | 0
Site Engineer | 52 | weeks |  | 0
Site Manager | 52 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 52 | weeks |  | 0
Labourer (including at handover) | 52 | weeks |  | 0
Quantity Surveying /Commercial Management | 52 | weeks |  | 0
Planner | 52 | weeks |  | 0
Health & Safety Officer | 52 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 52 | weeks |  | 0
Meeting room (inc furniture) | 52 | weeks |  | 0
Canteens and Kitchens | 52 | weeks |  | 0
Drying room | 52 | weeks |  | 0
Toilets and washrooms | 52 | weeks |  | 0
Secure stores | 52 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 52 | weeks |  | 0
IT systems with email and internet capability | 52 | weeks |  | 0
Consumables and services associated with site accommodation | 52 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 52 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks |  | 0
Gas Supply | 52 | weeks |  | 0
Electric supply, Lighting and power | 52 | weeks |  | 0
Drainage | 52 | weeks |  | 0
Security
Night watchman | 52 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 52 | weeks |  | 0
Material distribution
Forklift and driver | 26 | weeks |  | 0
Site plant
Small Dumper | 26 | weeks |  | 0
Mixer | 26 | weeks |  | 0
Road Sweeper including driver and fuel | 26 | weeks |  | 0
Excavator / mini digger including driver and fuel | 26 | weeks |  | 0
Small tools and equiptment | 26 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OHP | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 458350

## Low val Lot 4
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L4
TRADITIONAL CONSTRUCTION
LOCATION | North Yorkshire, West Yorkshire and East Yorkshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks |  | 0
Contracts Manager | 68 | weeks |  | 0
Site Engineer | 68 | weeks |  | 0
Site Manager | 68 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 68 | weeks |  | 0
Labourer (including at handover) | 68 | weeks |  | 0
Quantity Surveying / Commercial Management | 68 | weeks |  | 0
Planner | 68 | weeks |  | 0
Health & Safety Officer | 68 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 68 | weeks |  | 0
Meeting room (inc furniture) | 68 | weeks |  | 0
Canteens and Kitchens | 68 | weeks |  | 0
Drying room | 68 | weeks |  | 0
Toilets and washrooms | 68 | weeks |  | 0
Secure stores | 68 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 68 | weeks |  | 0
IT systems with email and internet capability | 68 | weeks |  | 0
Consumables and services associated with site accommodation | 68 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 68 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks |  | 0
Gas Supply | 68 | weeks |  | 0
Electric supply, Lighting and power | 68 | weeks |  | 0
Drainage | 68 | weeks |  | 0
Security
Night watchman | 68 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 68 | weeks |  | 0
Material distribution
Forklift and driver | 34 | weeks |  | 0
Site plant
Small Dumper | 34 | weeks |  | 0
Mixer | 34 | weeks |  | 0
Road Sweeper including driver and fuel | 34 | weeks |  | 0
Excavator / mini digger including driver and fuel | 34 | weeks |  | 0
Small tools and equiptment | 34 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L4
TIMBER FRAME CONSTRUCTION
LOCATION | North Yorkshire, West Yorkshire and East Yorkshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks |  | 0
Contracts Manager | 52 | weeks |  | 0
Site Engineer | 52 | weeks |  | 0
Site Manager | 52 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 52 | weeks |  | 0
Labourer (including at handover) | 52 | weeks |  | 0
Quantity Surveying /Commercial Management | 52 | weeks |  | 0
Planner | 52 | weeks |  | 0
Health & Safety Officer | 52 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 52 | weeks |  | 0
Meeting room (inc furniture) | 52 | weeks |  | 0
Canteens and Kitchens | 52 | weeks |  | 0
Drying room | 52 | weeks |  | 0
Toilets and washrooms | 52 | weeks |  | 0
Secure stores | 52 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 52 | weeks |  | 0
IT systems with email and internet capability | 52 | weeks |  | 0
Consumables and services associated with site accommodation | 52 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 52 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks |  | 0
Gas Supply | 52 | weeks |  | 0
Electric supply, Lighting and power | 52 | weeks |  | 0
Drainage | 52 | weeks |  | 0
Security
Night watchman | 52 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 52 | weeks |  | 0
Material distribution
Forklift and driver | 26 | weeks |  | 0
Site plant
Small Dumper | 26 | weeks |  | 0
Mixer | 26 | weeks |  | 0
Road Sweeper including driver and fuel | 26 | weeks |  | 0
Excavator / mini digger including driver and fuel | 26 | weeks |  | 0
Small tools and equiptment | 26 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OHP | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 458350

## Low val Lot 5
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L5
TRADITIONAL CONSTRUCTION
LOCATION | South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks |  | 0
Contracts Manager | 68 | weeks |  | 0
Site Engineer | 68 | weeks |  | 0
Site Manager | 68 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 68 | weeks |  | 0
Labourer (including at handover) | 68 | weeks |  | 0
Quantity Surveying / Commercial Management | 68 | weeks |  | 0
Planner | 68 | weeks |  | 0
Health & Safety Officer | 68 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 68 | weeks |  | 0
Meeting room (inc furniture) | 68 | weeks |  | 0
Canteens and Kitchens | 68 | weeks |  | 0
Drying room | 68 | weeks |  | 0
Toilets and washrooms | 68 | weeks |  | 0
Secure stores | 68 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 68 | weeks |  | 0
IT systems with email and internet capability | 68 | weeks |  | 0
Consumables and services associated with site accommodation | 68 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 68 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks |  | 0
Gas Supply | 68 | weeks |  | 0
Electric supply, Lighting and power | 68 | weeks |  | 0
Drainage | 68 | weeks |  | 0
Security
Night watchman | 68 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 68 | weeks |  | 0
Material distribution
Forklift and driver | 34 | weeks |  | 0
Site plant
Small Dumper | 34 | weeks |  | 0
Mixer | 34 | weeks |  | 0
Road Sweeper including driver and fuel | 34 | weeks |  | 0
Excavator / mini digger including driver and fuel | 34 | weeks |  | 0
Small tools and equiptment | 34 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L5
TIMBER FRAME CONSTRUCTION
LOCATION | South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks |  | 0
Contracts Manager | 52 | weeks |  | 0
Site Engineer | 52 | weeks |  | 0
Site Manager | 52 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 52 | weeks |  | 0
Labourer (including at handover) | 52 | weeks |  | 0
Quantity Surveying /Commercial Management | 52 | weeks |  | 0
Planner | 52 | weeks |  | 0
Health & Safety Officer | 52 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 52 | weeks |  | 0
Meeting room (inc furniture) | 52 | weeks |  | 0
Canteens and Kitchens | 52 | weeks |  | 0
Drying room | 52 | weeks |  | 0
Toilets and washrooms | 52 | weeks |  | 0
Secure stores | 52 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 52 | weeks |  | 0
IT systems with email and internet capability | 52 | weeks |  | 0
Consumables and services associated with site accommodation | 52 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 52 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks |  | 0
Gas Supply | 52 | weeks |  | 0
Electric supply, Lighting and power | 52 | weeks |  | 0
Drainage | 52 | weeks |  | 0
Security
Night watchman | 52 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 52 | weeks |  | 0
Material distribution
Forklift and driver | 26 | weeks |  | 0
Site plant
Small Dumper | 26 | weeks |  | 0
Mixer | 26 | weeks |  | 0
Road Sweeper including driver and fuel | 26 | weeks |  | 0
Excavator / mini digger including driver and fuel | 26 | weeks |  | 0
Small tools and equiptment | 26 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OHP | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 458350

## High val Lot 1
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | Countryside Partnerships
HIGH VALUE LOT H1 WEST
TRADITIONAL CONSTRUCTION
LOCATION | Greater Manchester, Merseyside, Cheshire, Derbyshire West, Staffordshire, Lancashire, Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 104 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 104 | weeks |  | 0 | not required for site this size
Contracts Manager | 104 | weeks | 675 | 70200 | 1/3 of time
Site Engineer | 104 | weeks | 100 | 10400 | overall allocation split by required duration
Site Manager | 104 | weeks | 1650 | 171600 | full time
Finishing Foreman / Assistant Site Manager | 104 | weeks | 931.5 | 96876 | 75% of time
Labourer (including at handover) | 104 | weeks | 650 | 67600 | number required based on Build requirements
Quantity Surveying / Commercial Management | 104 | weeks | 1211 | 125944 | (MQS/COM 25% £559, QS - 50% £652)
Planner | 104 | weeks | 100 | 10400 | overall allocation split by required duration
Health & Safety Officer | 104 | weeks | 0 | 0 | inc in overhead
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 5990 | 5990
Site office (inc furniture) | 104 | weeks | 85 | 8840
Meeting room (inc furniture) | 104 | weeks | 85 | 8840
Canteens and Kitchens | 104 | weeks | 100 | 10400
Drying room | 104 | weeks | 85 | 8840 | Split with canteen above
Toilets and washrooms | 104 | weeks | 85 | 8840
Secure stores | 104 | weeks | 38 | 3952 | 2no. Allowed
Telephones and Photocopiers (connection and charges) | 104 | weeks | 0 | 0
IT systems with email and internet capability | 104 | weeks | 0 | 0 | inc in o'head
Consumables and services associated with site accommodation | 104 | weeks | 50 | 5200
Fire points and fire fighting equipment | 1 | Item | 2000 | 2000
Main Contractor's Signboard | 1 | Item | 1500 | 1500
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 2000 | 2000
Cleaning
Site cleaning | 104 | weeks | 125 | 13000
Site set up
Tarmac and hardcore compound area | 1 | item | 10000 | 10000
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item | 5000 | 5000
Temproary fencing to compound area | 1 | item | 12500 | 12500
Temporary security fencing to site perimeter | 1 | item | 15725 | 15725 | measure based on site plan
Removal of compound on completion; reinstatement | 1 | item | 1500 | 1500
Temp Services incl all connections, disconnections and usage
Water supply | 104 | weeks | 64 | 6656 | Includes connection/disconnection
Gas Supply | 104 | weeks | 0 | 0 | Not required
Electric supply, Lighting and power | 104 | weeks | 238 | 24752 | Includes connection/disconnection
Drainage | 104 | weeks | 0 | 0
Security
Night watchman | 104 | weeks | 1534 | 159536
Pedestrian gates | 1 | item | 500 | 500
Vehicular gates | 1 | item | 1000 | 1000
CCTV cameras set up costs | 1 | item | 0 | 0
CCTV weekly charge | 104 | weeks | 450 | 46800
Material distribution
Forklift and driver | 52 | weeks | 1750 | 91000 | inc fuel - note that the no, of weeks is tbc
Site plant
Small Dumper | 52 | weeks | 0 | 0
Mixer | 52 | weeks | 0 | 0
Road Sweeper including driver and fuel | 52 | weeks | 500 | 26000 | Assumed 2nr visits per week
Excavator / mini digger including driver and fuel | 52 | weeks | 0 | 0
Small tools and equiptment | 52 | weeks | 150 | 7800 | we would have this for full duration of compound
Health and Safety
1st aid kit | 1 | item | 2000 | 2000
Health and safety site visits | 1 | item |  | 0 | inc in overhead
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item | 310769 | 310769
Adaption of Scaffolding | 1 | item | 0 | 0 | inc
Internal Scaffolding | 1 | item | 0 | 0 | inc
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 0 | 0
CDM regulations and health and safety plan | 1 | item | 0 | 0
Considerate constructors scheme | 1 | item | 2222 | 2222
SAP calculations and energy performance certificates | 1 | item | 4800 | 4800
Robust details | 1 | item | 2800 | 2800
Building Control Fees | 1 | item | 20000 | 20000
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 41679.444 | 41679.444 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 96000 | 96000 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0 | Site specific further details required
Concrete testing and reports | 1 | item | 0 | 0
Dilapidation Surveys | 1 | Item | 0 | 0
Sound testing | 1 | item | 0 | 0 | Not required as using Robust Details
Air pressure tests | 1 | item | 6800 | 6800
Handover costs
Snagging costs / inspections | 1 | item | 0 | 0
Contract cleaners | 1 | item | 36000 | 36000 | Allowance for cleaning per plot
Clean to external areas | 1 | item | 0 | 0
Skips | 15 | no | 225 | 3375
Lorry and tipping charges | 1 | item | 0 | 0
Resident handover packs | 80 | no | 0 | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item | 138645 | 138645 | 1.35% of overall build cost
6.5.1 Insurance | 1 | Item |  | 0 | inc in insurance above
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 80 | no | 500 | 40000
External areas - paths, paving and adopted areas | 1 | item | 2500 | 2500
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 1751781.444
Total of preliminaries expressed as a weekly cost |  |  |  | 16844.0523
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4.5%
Profit (expressed as a %) |  |  |  | 3%
Overheads and Profit Total |  |  |  | 7.5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 85 | 6086 | 3 | 18258
Superstructures
Superstructures | 71.6 | m2 | 602 | 43103.2 | 3 | 129309.6
Allowance for Part L June 22 uplift | 1 | item | 3105 | 3105 | 3 | 9315
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 156882.6
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 100 | 7160 | 16 | 114560
Superstructures
Superstructures | 71.6 | m2 | 660 | 47256 | 16 | 756096
Allowance for Part L June 22 uplift | 1 | item | 3105 | 3105 | 16 | 49680
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 920336
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 85 | 7242 | 7 | 50694
Superstructures
Superstructures | 85.2 | m2 | 583 | 49671.6 | 7 | 347701.2
Allowance for Part L June 22 uplift | 1 | item | 3350 | 3350 | 7 | 23450
Total cost for 3B4P mid mews houses (NDSS) | [5 empty] | 421845.2
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 100 | 8520 | 11 | 93720
Superstructures
Superstructures | 85.2 | m2 | 620 | 52824 | 11 | 581064
Allowance for Part L June 22 uplift | 1 | item | 3350 | 3350 | 11 | 36850
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 711634
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 100 | 8610 | 11 | 94710
Superstructures
Superstructures | 86.1 | m2 | 620 | 53382 | 11 | 587202
Allowance for Part L June 22 uplift | 1 | item | 3350 | 3350 | 11 | 36850
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 718762
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 100 | 9420 | 22 | 207240
Superstructures
Superstructures | 94.2 | m2 | 620 | 58404 | 22 | 1284888
Allowance for Part L June 22 uplift | 1 | item | 3350 | 3350 | 22 | 73700
Total cost for 3B5P houses (NDSS) | [5 empty] | 1565828
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 | 100 | 10830 | 10 | 108300
Superstructures
Superstructures | 108.3 | m2 | 575 | 62272.5 | 10 | 622725
Allowance for Part L June 22 uplift | 1 | item | 3850 | 3850 | 10 | 38500
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 769525
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² | 8.4 | 161128.8
Preparatory Groundworks | 19182 | m² | 0.25 | 4795.5
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² | 104.48 | 145122.72
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² | 73.26 | 74871.72
Non Adopted footpath (tarmac) including all edgings | 125 | m² | 62.86 | 7857.5
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² | 102.23 | 354431.41
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² | 99.75 | 212866.5
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² | 32.35 | 196202.75
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no | 145 | 12470
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm | 47 | 60254
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm | 60.23 | 23489.7
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item | 3465 | 277200
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 2258990.6
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 1751781.444
Substructure | [5 empty] | 687482
Superstructure | [5 empty] | 4308985.8
Part L Uplift | [5 empty] | 268345
External Works | [5 empty] | 2258990.6
Post Contract Design Fees at say 3% | [5 empty] | 278267.5453
OH&P | [5 empty] | 716538.9292
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 10270391.3185
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | Countryside Partnerships
HIGH VALUE LOT H1 WEST
TIMBER FRAME CONSTRUCTION
LOCATION | Greater Manchester, Merseyside, Cheshire, Derbyshire West, Staffordshire, Lancashire, Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 86 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 86 | weeks | 0 | 0 | not required for site this size
Contracts Manager | 86 | weeks | 675 | 58050 | 1/3 of time
Site Engineer | 86 | weeks | 100 | 8600 | overall allocation split by required duration
Site Manager | 86 | weeks | 1650 | 141900 | full time
Finishing Foreman / Assistant Site Manager | 86 | weeks | 931.5 | 80109 | 75% of time
Labourer (including at handover) | 86 | weeks | 650 | 55900 | number required based on Build requirements
Quantity Surveying /Commercial Management | 86 | weeks | 1211 | 104146 | (MQS/COM 25% £559, QS - 50% £652)
Planner | 86 | weeks | 100 | 8600 | overall allocation split by required duration
Health & Safety Officer | 86 | weeks | 0 | 0 | inc in overhead
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 5990 | 5990 | 0
Site office (inc furniture) | 86 | weeks | 85 | 7310 | 0
Meeting room (inc furniture) | 86 | weeks | 85 | 7310 | 0
Canteens and Kitchens | 86 | weeks | 100 | 8600 | 0
Drying room | 86 | weeks | 85 | 7310 | Split with canteen above
Toilets and washrooms | 86 | weeks | 85 | 7310 | 0
Secure stores | 86 | weeks | 38 | 3268 | 2no. Allowed
Telephones and Photocopiers (connection and charges) | 86 | weeks | 0 | 0 | 0
IT systems with email and internet capability | 86 | weeks | 0 | 0 | inc in o'head
Consumables and services associated with site accommodation | 86 | weeks | 50 | 4300 | 0
Fire points and fire fighting equipment | 1 | Item | 2000 | 2000 | 0
Main Contractor's Signboard | 1 | Item | 1500 | 1500 | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 2000 | 2000 | 0
Cleaning
Site cleaning | 86 | weeks | 125 | 10750 | 0
Site set up
Tarmac and hardcored compound area | 1 | item | 10000 | 10000 | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item | 5000 | 5000 | 0
Temproary fencing to compound area | 1 | item | 12500 | 12500 | 0
Temporary security fencing to site perimeter | 1 | item | 15725 | 15725 | measure based on site plan
Removal of compound on completion; reinstatement | 1 | item | 1500 | 1500 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 86 | weeks | 64 | 5504 | Includes connection/disconnection
Gas Supply | 86 | weeks | 0 | 0 | Not required
Electric supply, Lighting and power | 86 | weeks | 238 | 20468 | Includes connection/disconnection
Drainage | 86 | weeks | 0 | 0 | 0
Security
Night watchman | 86 | weeks | 1534 | 131924 | 0
Pedestrian gates | 1 | item | 500 | 500 | 0
Vehicular gates | 1 | item | 1000 | 1000 | 0
CCTV cameras set up costs | 1 | item | 0 | 0 | 0
CCTV weekly charge | 86 | weeks | 450 | 38700 | 0
Material distribution
Forklift and driver | 43 | weeks | 1750 | 75250 | inc fuel - note that the no, of weeks is tbc
Site plant
Small Dumper | 43 | weeks | 0 | 0 | 0
Mixer | 43 | weeks | 0 | 0 | 0
Road Sweeper including driver and fuel | 43 | weeks | 500 | 21500 | Assumed 2nr visits per week
Excavator / mini digger including driver and fuel | 43 | weeks | 0 | 0 | 0
Small tools and equiptment | 43 | weeks | 150 | 6450 | we would have this for full duration of compound
Health and Safety
1st aid kit | 1 | item | 2000 | 2000 | 0
Health and safety site visits | 1 | item | 0 | 0 | inc in overhead
Falling from heights | 1 | item | 0 | 0 | 0
Scaffolding
External scaffolding including mat | 1 | item | 297584.35 | 297584.35 | 0
Adaption of Scaffolding | 1 | item | 0 | 0 | inc
Internal Scaffolding | 1 | item | 0 | 0 | inc
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500 | 0
As built drawings and manuals | 1 | item | 0 | 0 | 0
CDM regulations and health and safety plan | 1 | item | 0 | 0 | 0
Considerate constructors scheme | 1 | item | 2222 | 2222 | 0
SAP calculations and energy performance certificates | 1 | item | 4800 | 4800 | 0
Robust details | 1 | item | 2800 | 2800 | 0
Building Control Fees | 1 | item | 20000 | 20000 | 0
Planning Condition Discharge Fees | 1 | item | 100 | 100 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 41679.444 | 41679.444 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 96000 | 96000 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0 | site specific tbc
Concrete testing and reports | 1 | item | 0 | 0 | 0
Dilapidation Surveys | 1 | Item | 0 | 0 | 0
Sound testing | 1 | item | 0 | 0 | robust details - not required
Air pressure tests | 1 | item | 6800 | 6800 | 0
Handover costs
Snagging costs | 1 | item | 0 | 0 | 0
Contract cleaners | 1 | item | 36000 | 36000 | Allowance for cleaning per plot
Clean to external areas | 1 | item | 0 | 0 | 0
Skips | 15 | no | 225 | 3375 | 0
Lorry and tipping charges | 1 | item | 0 | 0 | 0
Resident handover packs | 80 | no | 0 | 0 | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item | 141075 | 141075 | 1.35% of overall build cost
6.5.1 Insurance | 1 | Item | 0 | 0 | inc in insurance above
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 80 | no | 500 | 40000 | 0
External areas - paths, paving and adopted areas | 1 | item | 2500 | 2500 | 0
Landscaped areas | 1 | item | 0 | 0 | 0
Total of preliminaries |  |  |  | 1569409.794
Total of preliminaries expressed as a weekly cost |  |  |  | 18248.9511
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4.5%
Profit (expressed as a %) |  |  |  | 3%
Overheads and Profit Total |  |  |  | 7.5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 85.81 | 6143.996 | 3 | 18431.988
Superstructures
Superstructures | 71.6 | m2 | 641.5 | 45931.4 | 3 | 137794.2
Allowance for Part L June 22 uplift | 1 | item | 3105 | 3105 | 3 | 9315
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 165541.188
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 100.83 | 7219.428 | 16 | 115510.848
Superstructures
Superstructures | 71.6 | m2 | 699.5 | 50084.2 | 16 | 801347.2
Allowance for Part L June 22 uplift | 1 | item | 3105 | 3105 | 16 | 49680
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 966538.048
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 85.74 | 7305.048 | 7 | 51135.336
Superstructures
Superstructures | 85.2 | m2 | 629.28 | 53614.656 | 7 | 375302.592
Allowance for Part L June 22 uplift | 1 | item | 3380 | 3380 | 7 | 23660
Total cost for 3B4P mid mews houses (NDSS) | [5 empty] | 450097.928
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 100.69 | 8578.788 | 11 | 94366.668
Superstructures
Superstructures | 85.2 | m2 | 666.28 | 56767.056 | 11 | 624437.616
Allowance for Part L June 22 uplift | 1 | item | 3380 | 3380 | 11 | 37180
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 755984.284
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 101.84 | 8768.424 | 11 | 96452.664
Superstructures
Superstructures | 86.1 | m2 | 666.28 | 57366.708 | 11 | 631033.788
Allowance for Part L June 22 uplift | 1 | item | 3380 | 3380 | 11 | 37180
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 764666.452
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 100.67 | 9483.114 | 22 | 208628.508
Superstructures
Superstructures | 94.2 | m2 | 666.28 | 62763.576 | 22 | 1380798.672
Allowance for Part L June 22 uplift | 1 | item | 3380 | 3380 | 22 | 74360
Total cost for 3B5P houses (NDSS) | [5 empty] | 1663787.18
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 | 100.62 | 10897.146 | 10 | 108971.46
Superstructures
Superstructures | 108.3 | m2 | 643.67 | 69709.461 | 10 | 697094.61
Allowance for Part L June 22 uplift | 1 | item | 3730 | 3730 | 10 | 37300
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 843366.07
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² | 8.4 | 161128.8
Preparatory Groundworks | 19182 | m² | 0.25 | 4795.5
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² | 104.48 | 145122.72
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² | 73.26 | 74871.72
Non Adopted footpath (tarmac) including all edgings | 125 | m² | 62.86 | 7857.5
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² | 102.23 | 354431.41
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² | 99.75 | 212866.5
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² | 32.35 | 196202.75
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no | 145 | 12470
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm | 47 | 60254
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm | 60.23 | 23489.7
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item | 3465 | 277200
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 2258990.6
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 1569409.794
Substructure | [5 empty] | 693497.472
Superstructure | [5 empty] | 4647808.678
Part L Uplift | [5 empty] | 268675
External Works | [5 empty] | 2258990.6
Post Contract Design Fees at say 3% | [5 empty] | 283151.4463
OH&P | [5 empty] | 729114.9743
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 10450647.9646
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 10270391.3185
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 10450647.9646
TOTAL COMBINED SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 80 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 20721039.2831

## High val Lot 2
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | Countryside Partnerships
HIGH VALUE LOT H2 EAST
TRADITIONAL CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham, North Yorkshire, West Yorkshire, East Yorkshire, South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 104 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 104 | weeks | 0 | 0 | not required for site this size
Contracts Manager | 104 | weeks | 675 | 70200 | 1/3 of time
Site Engineer | 104 | weeks | 100 | 10400 | overall allocation split by required duration
Site Manager | 104 | weeks | 1750 | 182000 | full time
Finishing Foreman / Assistant Site Manager | 104 | weeks | 1012.5 | 105300 | 75% of time
Labourer (including at handover) | 104 | weeks | 625 | 65000 | number required based on Build requirements
Quantity Surveying / Commercial Management | 104 | weeks | 850 | 88400
Planner | 104 | weeks | 100 | 10400 | overall allocation split by required duration
Health & Safety Officer | 104 | weeks | 0 | 0 | inc in overhead
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 5990 | 5990
Site office (inc furniture) | 104 | weeks | 85 | 8840
Meeting room (inc furniture) | 104 | weeks | 85 | 8840
Canteens and Kitchens | 104 | weeks | 100 | 10400
Drying room | 104 | weeks | 85 | 8840 | Split with canteen above
Toilets and washrooms | 104 | weeks | 85 | 8840
Secure stores | 104 | weeks | 38 | 3952 | 2no. Allowed
Telephones and Photocopiers (connection and charges) | 104 | weeks | 0 | 0
IT systems with email and internet capability | 104 | weeks | 0 | 0 | inc in o'head
Consumables and services associated with site accommodation | 104 | weeks | 50 | 5200
Fire points and fire fighting equipment | 1 | Item | 2000 | 2000
Main Contractor's Signboard | 1 | Item | 1500 | 1500
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 2000 | 2000
Cleaning
Site cleaning | 104 | weeks | 125 | 13000
Site set up
Tarmac and hardcore compound area | 1 | item | 10000 | 10000
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item | 2500 | 2500
Temproary fencing to compound area | 1 | item | 5700 | 5700
Temporary security fencing to site perimeter | 1 | item | 7035 | 7035 | measure based on site plan
Removal of compound on completion; reinstatement | 1 | item | 1500 | 1500
Temp Services incl all connections, disconnections and usage
Water supply | 104 | weeks | 64 | 6656 | Includes connection/disconnection
Gas Supply | 104 | weeks | 0 | 0 | Not required
Electric supply, Lighting and power | 104 | weeks | 238 | 24752 | Includes connection/disconnection
Drainage | 104 | weeks | 0 | 0
Security
Night watchman | 104 | weeks | 1534 | 159536
Pedestrian gates | 1 | item | 250 | 250
Vehicular gates | 1 | item | 1000 | 1000
CCTV cameras set up costs | 1 | item | 0 | 0
CCTV weekly charge | 104 | weeks | 450 | 46800
Material distribution
Forklift and driver | 52 | weeks | 1090 | 56680 | note that the no, of weeks is tbc
Site plant
Small Dumper | 52 | weeks | 0 | 0
Mixer | 52 | weeks | 0 | 0
Road Sweeper including driver and fuel | 52 | weeks | 360 | 18720 | Assumed 2nr visits per week
Excavator / mini digger including driver and fuel | 52 | weeks | 0 | 0
Small tools and equiptment | 52 | weeks | 75 | 3900 | we would have this for full duration of compound
Health and Safety
1st aid kit | 1 | item | 2000 | 2000
Health and safety site visits | 1 | item | 0 | 0 | inc in overhead
Falling from heights | 1 | item | 0 | 0
Scaffolding
External scaffolding including mat | 1 | item | 178010 | 178010
Adaption of Scaffolding | 1 | item | 0 | 0
Internal Scaffolding | 1 | item | 52474 | 52474
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 0 | 0
CDM regulations and health and safety plan | 1 | item | 0 | 0
Considerate constructors scheme | 1 | item | 2222 | 2222
SAP calculations and energy performance certificates | 1 | item | 4800 | 4800
Robust details | 1 | item | 2800 | 2800
Building Control Fees | 1 | item | 20000 | 20000
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 46790 | 46790 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 92000 | 92000 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0 | Site specific further details required
Concrete testing and reports | 1 | item | 0 | 0
Dilapidation Surveys | 1 | Item | 0 | 0
Sound testing | 1 | item | 0 | 0 | Not required as using Robust Details
Air pressure tests | 1 | item | 6800 | 6800
Handover costs
Snagging costs / inspections | 1 | item | 0 | 0
Contract cleaners | 1 | item | 32000 | 32000 | Allowance for cleaning per plot
Clean to external areas | 1 | item | 0 | 0
Skips | 15 | no | 225 | 3375
Lorry and tipping charges | 1 | item | 0 | 0
Resident handover packs | 80 | no | 0 | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item | 132410 | 132410 | 1.35% of overall build cost
6.5.1 Insurance | 1 | Item | 0 | 0 | inc in insurance above
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 80 | no | 500 | 40000
External areas - paths, paving and adopted areas | 1 | item | 0 | 0
Landscaped areas | 1 | item | 0 | 0
Total of preliminaries |  |  |  | 1574812
Total of preliminaries expressed as a weekly cost |  |  |  | 15142.4231
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4.5%
Profit (expressed as a %) |  |  |  | 3%
Overheads and Profit Total |  |  |  | 7.5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 75.21 | 5385.036 | 3 | 16155.108
Superstructures
Superstructures | 71.6 | m2 | 595.35 | 42627.06 | 3 | 127881.18
Allowance for Part L June 22 uplift | 1 | item | 3105 | 3105 | 3 | 9315
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 153351.288
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 86.56 | 6197.696 | 16 | 99163.136
Superstructures
Superstructures | 71.6 | m2 | 678.19 | 48558.404 | 16 | 776934.464
Allowance for Part L June 22 uplift | 1 | item | 3105 | 3105 | 16 | 49680
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 925777.6
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 74.34 | 6333.768 | 7 | 44336.376
Superstructures
Superstructures | 85.2 | m2 | 552.83 | 47101.116 | 7 | 329707.812
Allowance for Part L June 22 uplift | 1 | item | 3350 | 3350 | 7 | 23450
Total cost for 3B4P mid mews houses (NDSS) | [5 empty] | 397494.188
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 81.3 | 6926.76 | 11 | 76194.36
Superstructures
Superstructures | 85.2 | m2 | 629.74 | 53653.848 | 11 | 590192.328
Allowance for Part L June 22 uplift | 1 | item | 3350 | 3350 | 11 | 36850
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 703236.688
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 79.72 | 6863.892 | 11 | 75502.812
Superstructures
Superstructures | 86.1 | m2 | 629.74 | 54220.614 | 11 | 596426.754
Allowance for Part L June 22 uplift | 1 | item | 3350 | 3350 | 11 | 36850
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 708779.566
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 80.32 | 7566.144 | 22 | 166455.168
Superstructures
Superstructures | 94.2 | m2 | 632.11 | 59544.762 | 22 | 1309984.764
Allowance for Part L June 22 uplift | 1 | item | 3350 | 3350 | 22 | 73700
Total cost for 3B5P houses (NDSS) | [5 empty] | 1550139.932
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 | 76.75 | 8312.025 | 10 | 83120.25
Superstructures
Superstructures | 108.3 | m2 | 553.41 | 59934.303 | 10 | 599343.03
Allowance for Part L June 22 uplift | 1 | item | 3850 | 3850 | 10 | 38500
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 720963.28
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² | 8.03 | 154031.46
Preparatory Groundworks | 19182 | m² | 0.25 | 4795.5
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² | 101.32 | 140733.48
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² | 69.2 | 70722.4
Non Adopted footpath (tarmac) including all edgings | 125 | m² | 86.95 | 10868.75
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² | 81.55 | 282733.85
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² | 101.1 | 215747.4
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² | 22.6 | 137069
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no | 135 | 11610
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm | 50 | 64100
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm | 60 | 23400
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item | 3500 | 280000
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 2124111.84
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 1574812
Substructure | [5 empty] | 560927.21
Superstructure | [5 empty] | 4330470.332
Part L Uplift | [5 empty] | 268345
External Works | [5 empty] | 2124111.84
Post Contract Design Fees at say 3% | [5 empty] | 265759.9915
OH&P | [5 empty] | 684331.978
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 9808758.3515
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | Countryside Partnerships
HIGH VALUE LOT H2 EAST
TIMBER FRAME CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham, North Yorkshire, West Yorkshire, East Yorkshire, South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 86 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 86 | weeks | 0 | 0 | not required for site this size
Contracts Manager | 86 | weeks | 675 | 58050 | 1/3 of time
Site Engineer | 86 | weeks | 100 | 8600 | overall allocation split by required duration
Site Manager | 86 | weeks | 1750 | 150500 | full time
Finishing Foreman / Assistant Site Manager | 86 | weeks | 1012.5 | 87075 | 75% of time
Labourer (including at handover) | 86 | weeks | 625 | 53750 | number required based on Build requirements
Quantity Surveying /Commercial Management | 86 | weeks | 850 | 73100 | 0
Planner | 86 | weeks | 100 | 8600 | overall allocation split by required duration
Health & Safety Officer | 86 | weeks | 0 | 0 | inc in overhead
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 5990 | 5990 | 0
Site office (inc furniture) | 86 | weeks | 85 | 7310 | 0
Meeting room (inc furniture) | 86 | weeks | 85 | 7310 | 0
Canteens and Kitchens | 86 | weeks | 100 | 8600 | 0
Drying room | 86 | weeks | 85 | 7310 | Split with canteen above
Toilets and washrooms | 86 | weeks | 85 | 7310 | 0
Secure stores | 86 | weeks | 38 | 3268 | 2no. Allowed
Telephones and Photocopiers (connection and charges) | 86 | weeks | 0 | 0 | 0
IT systems with email and internet capability | 86 | weeks | 0 | 0 | inc in o'head
Consumables and services associated with site accommodation | 86 | weeks | 50 | 4300 | 0
Fire points and fire fighting equipment | 1 | Item | 2000 | 2000 | 0
Main Contractor's Signboard | 1 | Item | 1500 | 1500 | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 2000 | 2000 | 0
Cleaning
Site cleaning | 86 | weeks | 125 | 10750 | 0
Site set up
Tarmac and hardcored compound area | 1 | item | 10000 | 10000 | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item | 2500 | 2500 | 0
Temproary fencing to compound area | 1 | item | 5700 | 5700 | 0
Temporary security fencing to site perimeter | 1 | item | 7035 | 7035 | measure based on site plan
Removal of compound on completion; reinstatement | 1 | item | 1500 | 1500 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 86 | weeks | 64 | 5504 | Includes connection/disconnection
Gas Supply | 86 | weeks | 0 | 0 | Not required
Electric supply, Lighting and power | 86 | weeks | 238 | 20468 | Includes connection/disconnection
Drainage | 86 | weeks | 0 | 0 | 0
Security
Night watchman | 86 | weeks | 1534 | 131924 | 0
Pedestrian gates | 1 | item | 250 | 250 | 0
Vehicular gates | 1 | item | 1000 | 1000 | 0
CCTV cameras set up costs | 1 | item | 0 | 0 | 0
CCTV weekly charge | 86 | weeks | 450 | 38700 | 0
Material distribution
Forklift and driver | 43 | weeks | 1090 | 46870 | note that the no, of weeks is tbc
Site plant
Small Dumper | 43 | weeks | 0 | 0 | 0
Mixer | 43 | weeks | 0 | 0 | 0
Road Sweeper including driver and fuel | 43 | weeks | 360 | 15480 | Assumed 2nr visits per week
Excavator / mini digger including driver and fuel | 43 | weeks | 0 | 0 | 0
Small tools and equiptment | 43 | weeks | 75 | 3225 | we would have this for full duration of compound
Health and Safety
1st aid kit | 1 | item | 2000 | 2000 | 0
Health and safety site visits | 1 | item | 0 | 0 | inc in overhead
Falling from heights | 1 | item | 0 | 0 | 0
Scaffolding
External scaffolding including mat | 1 | item | 223015 | 223015 | 0
Adaption of Scaffolding | 1 | item | 0 | 0 | 0
Internal Scaffolding | 1 | item | 0 | 0 | 0
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500 | 0
As built drawings and manuals | 1 | item | 0 | 0 | 0
CDM regulations and health and safety plan | 1 | item | 0 | 0 | 0
Considerate constructors scheme | 1 | item | 2222 | 2222 | 0
SAP calculations and energy performance certificates | 1 | item | 4800 | 4800 | 0
Robust details | 1 | item | 2800 | 2800 | 0
Building Control Fees | 1 | item | 20000 | 20000 | 0
Planning Condition Discharge Fees | 1 | item | 100 | 100 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 46790 | 46790 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 92000 | 92000 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0 | Site specific further details required
Concrete testing and reports | 1 | item | 0 | 0 | 0
Dilapidation Surveys | 1 | Item | 0 | 0 | 0
Sound testing | 1 | item | 0 | 0 | Not required as using Robust Details
Air pressure tests | 1 | item | 6800 | 6800 | 0
Handover costs
Snagging costs | 1 | item | 0 | 0 | 0
Contract cleaners | 1 | item | 32000 | 32000 | Allowance for cleaning per plot
Clean to external areas | 1 | item | 0 | 0 | 0
Skips | 15 | no | 225 | 3375 | 0
Lorry and tipping charges | 1 | item | 0 | 0 | 0
Resident handover packs | 80 | no | 0 | 0 | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item | 135518 | 135518 | 1.35% of overall build cost
6.5.1 Insurance | 1 | Item | 0 | 0 | inc in insurance above
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 80 | no | 500 | 40000 | 0
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | 0
Landscaped areas | 1 | item | 0 | 0 | 0
Total of preliminaries |  |  |  | 1410399
Total of preliminaries expressed as a weekly cost |  |  |  | 16399.9884
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4.5%
Profit (expressed as a %) |  |  |  | 3%
Overheads and Profit Total |  |  |  | 7.5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 76.02 | 5443.032 | 3 | 16329.096
Superstructures
Superstructures | 71.6 | m2 | 648.65 | 46443.34 | 3 | 139330.02
Allowance for Part L June 22 uplift | 1 | item | 3105 | 3105 | 3 | 9315
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 164974.116
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 87.39 | 6257.124 | 16 | 100113.984
Superstructures
Superstructures | 71.6 | m2 | 730.42 | 52298.072 | 16 | 836769.152
Allowance for Part L June 22 uplift | 1 | item | 3105 | 3105 | 16 | 49680
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 986563.136
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 75.08 | 6396.816 | 7 | 44777.712
Superstructures
Superstructures | 85.2 | m2 | 606.11 | 51640.572 | 7 | 361484.004
Allowance for Part L June 22 uplift | 1 | item | 3380 | 3380 | 7 | 23660
Total cost for 3B4P mid mews houses (Non NDSS) | [5 empty] | 429921.716
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 81.99 | 6985.548 | 11 | 76841.028
Superstructures
Superstructures | 85.2 | m2 | 681.94 | 58101.288 | 11 | 639114.168
Allowance for Part L June 22 uplift | 1 | item | 3380 | 3380 | 11 | 37180
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 753135.196
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 81.56 | 7022.316 | 11 | 77245.476
Superstructures
Superstructures | 86.1 | m2 | 681.96 | 58716.756 | 11 | 645884.316
Allowance for Part L June 22 uplift | 1 | item | 3380 | 3380 | 11 | 37180
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 760309.792
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 80.99 | 7629.258 | 22 | 167843.676
Superstructures
Superstructures | 94.2 | m2 | 684.32 | 64462.944 | 22 | 1418184.768
Allowance for Part L June 22 uplift | 1 | item | 3380 | 3380 | 22 | 74360
Total cost for 3B5P houses (Non NDSS) | [5 empty] | 1660388.444
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 | 77.37 | 8379.171 | 10 | 83791.71
Superstructures
Superstructures | 108.3 | m2 | 605.36 | 65560.488 | 10 | 655604.88
Allowance for Part L June 22 uplift | 1 | item | 3730 | 3730 | 10 | 37300
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 776696.59
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² | 8.03 | 154031.46
Preparatory Groundworks | 19182 | m² | 0.25 | 4795.5
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² | 101.32 | 140733.48
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² | 69.2 | 70722.4
Non Adopted footpath (tarmac) including all edgings | 125 | m² | 86.95 | 10868.75
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² | 81.55 | 282733.85
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² | 101.1 | 215747.4
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² | 22.6 | 137069
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no | 135 | 11610
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm | 50 | 64100
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm | 60 | 23400
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item | 3500 | 280000
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 2124111.84
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 1410399
Substructure | [5 empty] | 566942.682
Superstructure | [5 empty] | 4696371.308
Part L Uplift | [5 empty] | 268675
External Works | [5 empty] | 2124111.84
Post Contract Design Fees at say 3% | [5 empty] | 271994.9949
OH&P | [5 empty] | 700387.1119
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 10038881.9368
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 9808758.3515
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 10038881.9368
TOTAL COMBINED SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 80 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 19847640.2882