## Summary Sheet
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SUMMARY SHEET
TENDERER'S NAME | Whitfield & Brown (Developments) Ltd
SUMMARY OF TOTAL COMBINED COST FOR TIMBER FRAME AND TRADITIONAL CONSTRUCTION
LOT | COMBINED TOTAL
Low Value L1 | 9791933.5531
Low Value L2 | 9791933.5531
Low Value L3 | 458350
Low Value L4 | 458350
Low Value L5 | 458350
High Value H1 | 27161898.6723
High Value H2 | 1500298
NOTE: Where the 'Combined Total' cells above are highlighted red it is taken that the contractor is not tendering for the lot in question. Only pricing in the green highlighted cells will be taken forward.

## Low val Lot 1
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | Whitfield & Brown (Developments) Ltd
LOW VALUE LOT L1
TRADITIONAL CONSTRUCTION
LOCATION | Greater Manchester and Merseyside, Cheshire, Derbyshire West and Staffordshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks | 300 | 20400
Contracts Manager | 68 | weeks | 300 | 20400
Site Engineer | 68 | weeks | 50 | 3400
Site Manager | 68 | weeks | 1250 | 85000
Finishing Foreman / Assistant Site Manager | 68 | weeks | 250 | 17000
Labourer (including at handover) | 68 | weeks | 750 | 51000
Quantity Surveying / Commercial Management | 68 | weeks | 300 | 20400
Planner | 68 | weeks | 50 | 3400
Health & Safety Officer | 68 | weeks | 50 | 3400
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 2400 | 2400
Site office (inc furniture) | 68 | weeks | 55 | 3740
Meeting room (inc furniture) | 68 | weeks | 55 | 3740
Canteens and Kitchens | 68 | weeks | 55 | 3740
Drying room | 68 | weeks | 55 | 3740
Toilets and washrooms | 68 | weeks | 55 | 3740
Secure stores | 68 | weeks | 30 | 2040
Telephones and Photocopiers (connection and charges) | 68 | weeks | 50 | 3400
IT systems with email and internet capability | 68 | weeks | 50 | 3400
Consumables and services associated with site accommodation | 68 | weeks | 150 | 10200
Fire points and fire fighting equipment | 1 | Item | 500 | 500
Main Contractor's Signboard | 1 | Item | 1000 | 1000
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 1500 | 1500
Cleaning
Site cleaning | 68 | weeks | 80 | 5440
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0 | Included in Works Package
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0 | Included in Works Package
Temproary fencing to compound area | 1 | item |  | 0 | Included in Works Package
Temporary security fencing to site perimeter | 1 | item |  | 0 | Included in Works Package
Removal of compound on completion; reinstatement | 1 | item |  | 0 | Included in Works Package
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks | 100 | 6800
Gas Supply | 68 | weeks |  | 0
Electric supply, Lighting and power | 68 | weeks | 150 | 10200
Drainage | 68 | weeks | 20 | 1360
Security
Night watchman | 68 | weeks | 2350 | 159800
Pedestrian gates | 1 | item | 250 | 250
Vehicular gates | 1 | item | 500 | 500
CCTV cameras set up costs | 1 | item | 100 | 100
CCTV weekly charge | 68 | weeks | 350 | 23800
Material distribution
Forklift and driver | 34 | weeks |  | 0 | Included in Works Package
Site plant
Small Dumper | 34 | weeks |  | 0 | Included in Works Package
Mixer | 34 | weeks |  | 0 | Included in Works Package
Road Sweeper including driver and fuel | 34 | weeks |  | 0 | Included in Works Package
Excavator / mini digger including driver and fuel | 34 | weeks |  | 0 | Included in Works Package
Small tools and equiptment | 34 | weeks | 150 | 5100
Health and Safety
1st aid kit | 1 | item | 250 | 250
Health and safety site visits | 1 | item | 2000 | 2000
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0 | Included in Works Package
Adaption of Scaffolding | 1 | item |  | 0 | Included in Works Package
Internal Scaffolding | 1 | item |  | 0 | Included in Works Package
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 250 | 250
CDM regulations and health and safety plan | 1 | item | 250 | 250
Considerate constructors scheme | 1 | item | 1000 | 1000
SAP calculations and energy performance certificates | 1 | item | 2500 | 2500
Robust details | 1 | item | 500 | 500
Building Control Fees | 1 | item | 7500 | 7500
Planning Condition Discharge Fees | 15 | no | 150 | 2250 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 15000 | 15000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 54000 | 54000 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0 | Included in Works Package
Concrete testing and reports | 1 | item |  | 0 | Included in Works Package
Dilapidation Surveys | 1 | Item |  | 0 | Included in Works Package
Sound testing | 1 | item | 1000 | 1000
Air pressure tests | 1 | item | 1500 | 1500
Handover costs
Snagging costs / inspections | 1 | item |  | 0 | Included
Contract cleaners | 1 | item | 9450 | 9450
Clean to external areas | 1 | item |  | 0 | Included
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item |  | 0 | Included in Works Package
Resident handover packs | 27 | no | 50 | 1350
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0 | TBA - Job Specific
6.5.1 Insurance | 1 | Item |  | 0 | TBA - Job Specific
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no |  | 0 | Included
External areas - paths, paving and adopted areas | 1 | item |  | 0 | Included
Landscaped areas | 1 | item |  | 0 | Included
Total of preliminaries |  |  |  | 582790
Total of preliminaries expressed as a weekly cost |  |  |  | 8570.4412
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 3%
Profit (expressed as a %) |  |  |  | 2%
Overheads and Profit Total |  |  |  | 5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 164 | 11742.4 | 3 | 35227.2
Superstructures
Superstructures | 71.6 | m2 | 1082 | 77471.2 | 3 | 232413.6
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 3 | 15000
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 282640.8
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 164 | 11742.4 | 5 | 58712
Superstructures
Superstructures | 71.6 | m2 | 1082 | 77471.2 | 5 | 387356
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 5 | 25000
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 471068
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 164 | 13972.8 | 10 | 139728
Superstructures
Superstructures | 85.2 | m2 | 1082 | 92186.4 | 10 | 921864
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 10 | 50000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1111592
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 164 | 14120.4 | 3 | 42361.2
Superstructures
Superstructures | 86.1 | m2 | 1082 | 93160.2 | 3 | 279480.6
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 3 | 15000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 336841.8
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 164 | 15448.8 | 6 | 92692.8
Superstructures
Superstructures | 94.2 | m2 | 1082 | 101924.4 | 6 | 611546.4
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 6 | 30000
Total cost for 3B5P houses (NDSS) | [5 empty] | 734239.2
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 12.5 | 99275
Preparatory Groundworks | 7942 | m² | 1 | 7942
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 167.5 | 136345
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 145.8 | 86313.6
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 135 | 121500
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 105 | 128625
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 25.8 | 68086.2
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 195 | 5655
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 75 | 38025
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 95 | 38095
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 1500 | 40500
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 992861.8
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 582790
Substructure | [5 empty] | 368721.2
Superstructure | [5 empty] | 2432660.6
Part L Uplift | [5 empty] | 135000
External Works | [5 empty] | 992861.8
Post Contract Design Fees at say 3% | [5 empty] | 135361.008
OH&P | [5 empty] | 232369.7304
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4879764.3384
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | Whitfield & Brown (Developments) Ltd
LOW VALUE LOT L1
TIMBER FRAME CONSTRUCTION
LOCATION | Greater Manchester and Merseyside, Cheshire, Derbyshire West and Staffordshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks | 300 | 15600
Contracts Manager | 52 | weeks | 300 | 15600
Site Engineer | 52 | weeks | 50 | 2600
Site Manager | 52 | weeks | 1250 | 65000
Finishing Foreman / Assistant Site Manager | 52 | weeks | 250 | 13000
Labourer (including at handover) | 52 | weeks | 750 | 39000
Quantity Surveying /Commercial Management | 52 | weeks | 300 | 15600
Planner | 52 | weeks | 50 | 2600
Health & Safety Officer | 52 | weeks | 50 | 2600
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 2400 | 2400
Site office (inc furniture) | 52 | weeks | 55 | 2860
Meeting room (inc furniture) | 52 | weeks | 55 | 2860
Canteens and Kitchens | 52 | weeks | 55 | 2860
Drying room | 52 | weeks | 55 | 2860
Toilets and washrooms | 52 | weeks | 55 | 2860
Secure stores | 52 | weeks | 30 | 1560
Telephones and Photocopiers (connection and charges) | 52 | weeks | 50 | 2600
IT systems with email and internet capability | 52 | weeks | 50 | 2600
Consumables and services associated with site accommodation | 52 | weeks | 150 | 7800
Fire points and fire fighting equipment | 1 | Item | 500 | 500
Main Contractor's Signboard | 1 | Item | 1000 | 1000
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 1500 | 1500
Cleaning
Site cleaning | 52 | weeks | 80 | 4160
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0 | Included in Works Package
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0 | Included in Works Package
Temproary fencing to compound area | 1 | item |  | 0 | Included in Works Package
Temporary security fencing to site perimeter | 1 | item |  | 0 | Included in Works Package
Removal of compound on completion; reinstatement | 1 | item |  | 0 | Included in Works Package
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks | 100 | 5200
Gas Supply | 52 | weeks |  | 0
Electric supply, Lighting and power | 52 | weeks | 150 | 7800
Drainage | 52 | weeks | 20 | 1040
Security
Night watchman | 52 | weeks | 2350 | 122200
Pedestrian gates | 1 | item | 250 | 250
Vehicular gates | 1 | item | 500 | 500
CCTV cameras set up costs | 1 | item | 100 | 100
CCTV weekly charge | 52 | weeks | 350 | 18200
Material distribution
Forklift and driver | 26 | weeks |  | 0 | Included in works package
Site plant
Small Dumper | 26 | weeks |  | 0 | Included in works package
Mixer | 26 | weeks |  | 0 | Included in works package
Road Sweeper including driver and fuel | 26 | weeks |  | 0 | Included in works package
Excavator / mini digger including driver and fuel | 26 | weeks |  | 0 | Included in works package
Small tools and equiptment | 26 | weeks | 150 | 3900
Health and Safety
1st aid kit | 1 | item | 250 | 250
Health and safety site visits | 1 | item | 2000 | 2000
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0 | Included in works package
Adaption of Scaffolding | 1 | item |  | 0 | Included in works package
Internal Scaffolding | 1 | item |  | 0 | Included in works package
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 250 | 250
CDM regulations and health and safety plan | 1 | item | 250 | 250
Considerate constructors scheme | 1 | item | 1000 | 1000
SAP calculations and energy performance certificates | 1 | item | 2500 | 2500
Robust details | 1 | item | 500 | 500
Building Control Fees | 1 | item | 7500 | 7500
Planning Condition Discharge Fees | 15 | no | 150 | 2250 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 15000 | 15000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 54000 | 54000 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0 | Included in works package
Concrete testing and reports | 1 | item |  | 0 | Included in works package
Dilapidation Surveys | 1 | Item |  | 0 | Included in works package
Sound testing | 1 | item | 1000 | 1000
Air pressure tests | 1 | item | 1500 | 1500
Handover costs
Snagging costs | 1 | item |  | 0 | Included
Contract cleaners | 1 | item | 9450 | 9450
Clean to external areas | 1 | item |  | 0 | Included
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item |  | 0 | Included
Resident handover packs | 27 | no | 50 | 1350
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0 | TBA Job Specific
6.5.1 Insurance | 1 | Item |  | 0 | TBA Job Specific
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no |  | 0 | Included
External areas - paths, paving and adopted areas | 1 | item |  | 0 | Included
Landscaped areas | 1 | item |  | 0 | Included
Total of preliminaries |  |  |  | 471110
Total of preliminaries expressed as a weekly cost |  |  |  | 9059.8077
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 3%
Profit (expressed as a %) |  |  |  | 2%
Overheads and Profit Total |  |  |  | 5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 164 | 11742.4 | 3 | 35227.2
Superstructures
Superstructures | 71.6 | m2 | 1145 | 81982 | 3 | 245946
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 3 | 15000
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 296173.2
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 164 | 11742.4 | 5 | 58712
Superstructures
Superstructures | 71.6 | m2 | 1145 | 81982 | 5 | 409910
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 5 | 25000
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 493622
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 164 | 13972.8 | 10 | 139728
Superstructures
Superstructures | 85.2 | m2 | 1145 | 97554 | 10 | 975540
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 10 | 50000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1165268
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 164 | 14120.4 | 3 | 42361.2
Superstructures
Superstructures | 86.1 | m2 | 1145 | 98584.5 | 3 | 295753.5
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 3 | 15000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 353114.7
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 164 | 15448.8 | 6 | 92692.8
Superstructures
Superstructures | 94.2 | m2 | 1145 | 107859 | 6 | 647154
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 6 | 30000
Total cost for 3B5P houses (NDSS) | [5 empty] | 769846.8
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 12.5 | 99275
Preparatory Groundworks | 7942 | m² | 1 | 7942
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 167.5 | 136345
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 145.8 | 86313.6
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 135 | 121500
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 105 | 128625
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 25.8 | 68086.2
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 195 | 5655
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 75 | 38025
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 95 | 38095
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 1500 | 40500
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 992861.8
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 471110
Substructure | [5 empty] | 368721.2
Superstructure | [5 empty] | 2574303.5
Part L Uplift | [5 empty] | 135000
External Works | [5 empty] | 992861.8
Post Contract Design Fees at say 3% | [5 empty] | 136259.895
OHP | [5 empty] | 233912.8197
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4912169.2147
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4879764.3384
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4912169.2147
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 9791933.5531

## Low val Lot 2
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | Whitfield & Brown (Developments) Ltd
LOW VALUE LOT L2
TRADITIONAL CONSTRUCTION
LOCATION | Lancashire and Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks | 300 | 20400
Contracts Manager | 68 | weeks | 300 | 20400
Site Engineer | 68 | weeks | 50 | 3400
Site Manager | 68 | weeks | 1250 | 85000
Finishing Foreman / Assistant Site Manager | 68 | weeks | 250 | 17000
Labourer (including at handover) | 68 | weeks | 750 | 51000
Quantity Surveying / Commercial Management | 68 | weeks | 300 | 20400
Planner | 68 | weeks | 50 | 3400
Health & Safety Officer | 68 | weeks | 50 | 3400
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 2400 | 2400
Site office (inc furniture) | 68 | weeks | 55 | 3740
Meeting room (inc furniture) | 68 | weeks | 55 | 3740
Canteens and Kitchens | 68 | weeks | 55 | 3740
Drying room | 68 | weeks | 55 | 3740
Toilets and washrooms | 68 | weeks | 55 | 3740
Secure stores | 68 | weeks | 30 | 2040
Telephones and Photocopiers (connection and charges) | 68 | weeks | 50 | 3400
IT systems with email and internet capability | 68 | weeks | 50 | 3400
Consumables and services associated with site accommodation | 68 | weeks | 150 | 10200
Fire points and fire fighting equipment | 1 | Item | 500 | 500
Main Contractor's Signboard | 1 | Item | 1000 | 1000
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 1500 | 1500
Cleaning
Site cleaning | 68 | weeks | 80 | 5440
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0 | Included in Works Package
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0 | Included in Works Package
Temproary fencing to compound area | 1 | item |  | 0 | Included in Works Package
Temporary security fencing to site perimeter | 1 | item |  | 0 | Included in Works Package
Removal of compound on completion; reinstatement | 1 | item |  | 0 | Included in Works Package
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks | 100 | 6800
Gas Supply | 68 | weeks |  | 0
Electric supply, Lighting and power | 68 | weeks | 150 | 10200
Drainage | 68 | weeks | 20 | 1360
Security
Night watchman | 68 | weeks | 2350 | 159800
Pedestrian gates | 1 | item | 250 | 250
Vehicular gates | 1 | item | 500 | 500
CCTV cameras set up costs | 1 | item | 100 | 100
CCTV weekly charge | 68 | weeks | 350 | 23800
Material distribution
Forklift and driver | 34 | weeks |  | 0 | Included in Works Package
Site plant
Small Dumper | 34 | weeks |  | 0 | Included in Works Package
Mixer | 34 | weeks |  | 0 | Included in Works Package
Road Sweeper including driver and fuel | 34 | weeks |  | 0 | Included in Works Package
Excavator / mini digger including driver and fuel | 34 | weeks |  | 0 | Included in Works Package
Small tools and equiptment | 34 | weeks | 150 | 5100
Health and Safety
1st aid kit | 1 | item | 250 | 250
Health and safety site visits | 1 | item | 2000 | 2000
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0 | Included in Works Package
Adaption of Scaffolding | 1 | item |  | 0 | Included in Works Package
Internal Scaffolding | 1 | item |  | 0 | Included in Works Package
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 250 | 250
CDM regulations and health and safety plan | 1 | item | 250 | 250
Considerate constructors scheme | 1 | item | 1000 | 1000
SAP calculations and energy performance certificates | 1 | item | 2500 | 2500
Robust details | 1 | item | 500 | 500
Building Control Fees | 1 | item | 7500 | 7500
Planning Condition Discharge Fees | 15 | no | 150 | 2250 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 15000 | 15000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 54000 | 54000 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0 | Included in Works Package
Concrete testing and reports | 1 | item |  | 0 | Included in Works Package
Dilapidation Surveys | 1 | Item |  | 0 | Included in Works Package
Sound testing | 1 | item | 1000 | 1000
Air pressure tests | 1 | item | 1500 | 1500
Handover costs
Snagging costs / inspections | 1 | item |  | 0 | Included
Contract cleaners | 1 | item | 9450 | 9450
Clean to external areas | 1 | item |  | 0 | Included
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item |  | 0 | Included
Resident handover packs | 27 | no | 50 | 1350
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0 | TBA - Job Specific
6.5.1 Insurance | 1 | Item |  | 0 | TBA - Job Specific
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no |  | 0 | Included
External areas - paths, paving and adopted areas | 1 | item |  | 0 | Included
Landscaped areas | 1 | item |  | 0 | Included
Total of preliminaries |  |  |  | 582790
Total of preliminaries expressed as a weekly cost |  |  |  | 8570.4412
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 3%
Profit (expressed as a %) |  |  |  | 2%
Overheads and Profit Total |  |  |  | 5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 164 | 11742.4 | 3 | 35227.2
Superstructures
Superstructures | 71.6 | m2 | 1082 | 77471.2 | 3 | 232413.6
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 3 | 15000
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 282640.8
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 164 | 11742.4 | 5 | 58712
Superstructures
Superstructures | 71.6 | m2 | 1082 | 77471.2 | 5 | 387356
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 5 | 25000
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 471068
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 164 | 13972.8 | 10 | 139728
Superstructures
Superstructures | 85.2 | m2 | 1082 | 92186.4 | 10 | 921864
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 10 | 50000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1111592
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 164 | 14120.4 | 3 | 42361.2
Superstructures
Superstructures | 86.1 | m2 | 1082 | 93160.2 | 3 | 279480.6
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 3 | 15000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 336841.8
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 164 | 15448.8 | 6 | 92692.8
Superstructures
Superstructures | 94.2 | m2 | 1082 | 101924.4 | 6 | 611546.4
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 6 | 30000
Total cost for 3B5P houses (NDSS) | [5 empty] | 734239.2
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 12.5 | 99275
Preparatory Groundworks | 7942 | m² | 1 | 7942
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 167.5 | 136345
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 145.8 | 86313.6
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 135 | 121500
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 105 | 128625
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 25.8 | 68086.2
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 195 | 5655
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 75 | 38025
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 95 | 38095
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 1500 | 40500
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 992861.8
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 582790
Substructure | [5 empty] | 368721.2
Superstructure | [5 empty] | 2432660.6
Part L Uplift | [5 empty] | 135000
External Works | [5 empty] | 992861.8
Post Contract Design Fees at say 3% | [5 empty] | 135361.008
OH&P | [5 empty] | 232369.7304
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4879764.3384
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | Whitfield & Brown (Developments) Ltd
LOW VALUE LOT L2
TIMBER FRAME CONSTRUCTION
LOCATION | Lancashire and Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks | 300 | 15600
Contracts Manager | 52 | weeks | 300 | 15600
Site Engineer | 52 | weeks | 50 | 2600
Site Manager | 52 | weeks | 1250 | 65000
Finishing Foreman / Assistant Site Manager | 52 | weeks | 250 | 13000
Labourer (including at handover) | 52 | weeks | 750 | 39000
Quantity Surveying /Commercial Management | 52 | weeks | 300 | 15600
Planner | 52 | weeks | 50 | 2600
Health & Safety Officer | 52 | weeks | 50 | 2600
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 2400 | 2400
Site office (inc furniture) | 52 | weeks | 55 | 2860
Meeting room (inc furniture) | 52 | weeks | 55 | 2860
Canteens and Kitchens | 52 | weeks | 55 | 2860
Drying room | 52 | weeks | 55 | 2860
Toilets and washrooms | 52 | weeks | 55 | 2860
Secure stores | 52 | weeks | 30 | 1560
Telephones and Photocopiers (connection and charges) | 52 | weeks | 50 | 2600
IT systems with email and internet capability | 52 | weeks | 50 | 2600
Consumables and services associated with site accommodation | 52 | weeks | 150 | 7800
Fire points and fire fighting equipment | 1 | Item | 500 | 500
Main Contractor's Signboard | 1 | Item | 1000 | 1000
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 1500 | 1500
Cleaning
Site cleaning | 52 | weeks | 80 | 4160
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0 | Included in Works Package
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0 | Included in Works Package
Temproary fencing to compound area | 1 | item |  | 0 | Included in Works Package
Temporary security fencing to site perimeter | 1 | item |  | 0 | Included in Works Package
Removal of compound on completion; reinstatement | 1 | item |  | 0 | Included in Works Package
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks | 100 | 5200
Gas Supply | 52 | weeks |  | 0 | N/A
Electric supply, Lighting and power | 52 | weeks | 150 | 7800
Drainage | 52 | weeks | 20 | 1040
Security
Night watchman | 52 | weeks | 2350 | 122200
Pedestrian gates | 1 | item | 250 | 250
Vehicular gates | 1 | item | 500 | 500
CCTV cameras set up costs | 1 | item | 100 | 100
CCTV weekly charge | 52 | weeks | 350 | 18200
Material distribution
Forklift and driver | 26 | weeks |  | 0 | Included in works package
Site plant
Small Dumper | 26 | weeks |  | 0 | Included in works package
Mixer | 26 | weeks |  | 0 | Included in works package
Road Sweeper including driver and fuel | 26 | weeks |  | 0 | Included in works package
Excavator / mini digger including driver and fuel | 26 | weeks |  | 0 | Included in works package
Small tools and equiptment | 26 | weeks | 150 | 3900
Health and Safety
1st aid kit | 1 | item | 250 | 250
Health and safety site visits | 1 | item | 2000 | 2000
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0 | Included in works package
Adaption of Scaffolding | 1 | item |  | 0 | Included in works package
Internal Scaffolding | 1 | item |  | 0 | Included in works package
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 250 | 250
CDM regulations and health and safety plan | 1 | item | 250 | 250
Considerate constructors scheme | 1 | item | 1000 | 1000
SAP calculations and energy performance certificates | 1 | item | 2500 | 2500
Robust details | 1 | item | 500 | 500
Building Control Fees | 1 | item | 7500 | 7500
Planning Condition Discharge Fees | 15 | no | 150 | 2250 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 15000 | 15000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 54000 | 54000 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0 | Included in works package
Concrete testing and reports | 1 | item |  | 0 | Included in works package
Dilapidation Surveys | 1 | Item |  | 0 | Included in works package
Sound testing | 1 | item | 1000 | 1000
Air pressure tests | 1 | item | 1500 | 1500
Handover costs
Snagging costs | 1 | item |  | 0 | Included
Contract cleaners | 1 | item | 9450 | 9450
Clean to external areas | 1 | item |  | 0 | Included
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item |  | 0 | Included in works package
Resident handover packs | 27 | no | 50 | 1350
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0 | TBA - Job Specific
6.5.1 Insurance | 1 | Item |  | 0 | TBA - Job Specific
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no |  | 0 | Included
External areas - paths, paving and adopted areas | 1 | item |  | 0 | Included
Landscaped areas | 1 | item |  | 0 | Included
Total of preliminaries |  |  |  | 471110
Total of preliminaries expressed as a weekly cost |  |  |  | 9059.8077
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 3%
Profit (expressed as a %) |  |  |  | 2%
Overheads and Profit Total |  |  |  | 5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 164 | 11742.4 | 3 | 35227.2
Superstructures
Superstructures | 71.6 | m2 | 1145 | 81982 | 3 | 245946
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 3 | 15000
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 296173.2
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 164 | 11742.4 | 5 | 58712
Superstructures
Superstructures | 71.6 | m2 | 1145 | 81982 | 5 | 409910
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 5 | 25000
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 493622
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 164 | 13972.8 | 10 | 139728
Superstructures
Superstructures | 85.2 | m2 | 1145 | 97554 | 10 | 975540
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 10 | 50000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1165268
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 164 | 14120.4 | 3 | 42361.2
Superstructures
Superstructures | 86.1 | m2 | 1145 | 98584.5 | 3 | 295753.5
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 3 | 15000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 353114.7
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 164 | 15448.8 | 6 | 92692.8
Superstructures
Superstructures | 94.2 | m2 | 1145 | 107859 | 6 | 647154
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 6 | 30000
Total cost for 3B5P houses (NDSS) | [5 empty] | 769846.8
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 12.5 | 99275
Preparatory Groundworks | 7942 | m² | 1 | 7942
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 167.5 | 136345
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 145.8 | 86313.6
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 135 | 121500
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 105 | 128625
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 25.8 | 68086.2
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 195 | 5655
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 75 | 38025
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 95 | 38095
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 1500 | 40500
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 992861.8
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 471110
Substructure | [5 empty] | 368721.2
Superstructure | [5 empty] | 2574303.5
Part L Uplift | [5 empty] | 135000
External Works | [5 empty] | 992861.8
Post Contract Design Fees at say 3% | [5 empty] | 136259.895
OHP | [5 empty] | 233912.8197
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4912169.2147
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4879764.3384
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4912169.2147
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 9791933.5531

## Low val Lot 3
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L3
TRADITIONAL CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks |  | 0
Contracts Manager | 68 | weeks |  | 0
Site Engineer | 68 | weeks |  | 0
Site Manager | 68 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 68 | weeks |  | 0
Labourer (including at handover) | 68 | weeks |  | 0
Quantity Surveying / Commercial Management | 68 | weeks |  | 0
Planner | 68 | weeks |  | 0
Health & Safety Officer | 68 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 68 | weeks |  | 0
Meeting room (inc furniture) | 68 | weeks |  | 0
Canteens and Kitchens | 68 | weeks |  | 0
Drying room | 68 | weeks |  | 0
Toilets and washrooms | 68 | weeks |  | 0
Secure stores | 68 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 68 | weeks |  | 0
IT systems with email and internet capability | 68 | weeks |  | 0
Consumables and services associated with site accommodation | 68 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 68 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks |  | 0
Gas Supply | 68 | weeks |  | 0
Electric supply, Lighting and power | 68 | weeks |  | 0
Drainage | 68 | weeks |  | 0
Security
Night watchman | 68 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 68 | weeks |  | 0
Material distribution
Forklift and driver | 34 | weeks |  | 0
Site plant
Small Dumper | 34 | weeks |  | 0
Mixer | 34 | weeks |  | 0
Road Sweeper including driver and fuel | 34 | weeks |  | 0
Excavator / mini digger including driver and fuel | 34 | weeks |  | 0
Small tools and equiptment | 34 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L3
TIMBER FRAME CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks |  | 0
Contracts Manager | 52 | weeks |  | 0
Site Engineer | 52 | weeks |  | 0
Site Manager | 52 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 52 | weeks |  | 0
Labourer (including at handover) | 52 | weeks |  | 0
Quantity Surveying /Commercial Management | 52 | weeks |  | 0
Planner | 52 | weeks |  | 0
Health & Safety Officer | 52 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 52 | weeks |  | 0
Meeting room (inc furniture) | 52 | weeks |  | 0
Canteens and Kitchens | 52 | weeks |  | 0
Drying room | 52 | weeks |  | 0
Toilets and washrooms | 52 | weeks |  | 0
Secure stores | 52 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 52 | weeks |  | 0
IT systems with email and internet capability | 52 | weeks |  | 0
Consumables and services associated with site accommodation | 52 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 52 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks |  | 0
Gas Supply | 52 | weeks |  | 0
Electric supply, Lighting and power | 52 | weeks |  | 0
Drainage | 52 | weeks |  | 0
Security
Night watchman | 52 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 52 | weeks |  | 0
Material distribution
Forklift and driver | 26 | weeks |  | 0
Site plant
Small Dumper | 26 | weeks |  | 0
Mixer | 26 | weeks |  | 0
Road Sweeper including driver and fuel | 26 | weeks |  | 0
Excavator / mini digger including driver and fuel | 26 | weeks |  | 0
Small tools and equiptment | 26 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OHP | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 458350

## Low val Lot 4
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L4
TRADITIONAL CONSTRUCTION
LOCATION | North Yorkshire, West Yorkshire and East Yorkshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks |  | 0
Contracts Manager | 68 | weeks |  | 0
Site Engineer | 68 | weeks |  | 0
Site Manager | 68 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 68 | weeks |  | 0
Labourer (including at handover) | 68 | weeks |  | 0
Quantity Surveying / Commercial Management | 68 | weeks |  | 0
Planner | 68 | weeks |  | 0
Health & Safety Officer | 68 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 68 | weeks |  | 0
Meeting room (inc furniture) | 68 | weeks |  | 0
Canteens and Kitchens | 68 | weeks |  | 0
Drying room | 68 | weeks |  | 0
Toilets and washrooms | 68 | weeks |  | 0
Secure stores | 68 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 68 | weeks |  | 0
IT systems with email and internet capability | 68 | weeks |  | 0
Consumables and services associated with site accommodation | 68 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 68 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks |  | 0
Gas Supply | 68 | weeks |  | 0
Electric supply, Lighting and power | 68 | weeks |  | 0
Drainage | 68 | weeks |  | 0
Security
Night watchman | 68 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 68 | weeks |  | 0
Material distribution
Forklift and driver | 34 | weeks |  | 0
Site plant
Small Dumper | 34 | weeks |  | 0
Mixer | 34 | weeks |  | 0
Road Sweeper including driver and fuel | 34 | weeks |  | 0
Excavator / mini digger including driver and fuel | 34 | weeks |  | 0
Small tools and equiptment | 34 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L4
TIMBER FRAME CONSTRUCTION
LOCATION | North Yorkshire, West Yorkshire and East Yorkshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks |  | 0
Contracts Manager | 52 | weeks |  | 0
Site Engineer | 52 | weeks |  | 0
Site Manager | 52 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 52 | weeks |  | 0
Labourer (including at handover) | 52 | weeks |  | 0
Quantity Surveying /Commercial Management | 52 | weeks |  | 0
Planner | 52 | weeks |  | 0
Health & Safety Officer | 52 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 52 | weeks |  | 0
Meeting room (inc furniture) | 52 | weeks |  | 0
Canteens and Kitchens | 52 | weeks |  | 0
Drying room | 52 | weeks |  | 0
Toilets and washrooms | 52 | weeks |  | 0
Secure stores | 52 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 52 | weeks |  | 0
IT systems with email and internet capability | 52 | weeks |  | 0
Consumables and services associated with site accommodation | 52 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 52 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks |  | 0
Gas Supply | 52 | weeks |  | 0
Electric supply, Lighting and power | 52 | weeks |  | 0
Drainage | 52 | weeks |  | 0
Security
Night watchman | 52 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 52 | weeks |  | 0
Material distribution
Forklift and driver | 26 | weeks |  | 0
Site plant
Small Dumper | 26 | weeks |  | 0
Mixer | 26 | weeks |  | 0
Road Sweeper including driver and fuel | 26 | weeks |  | 0
Excavator / mini digger including driver and fuel | 26 | weeks |  | 0
Small tools and equiptment | 26 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OHP | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 458350

## Low val Lot 5
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L5
TRADITIONAL CONSTRUCTION
LOCATION | South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks |  | 0
Contracts Manager | 68 | weeks |  | 0
Site Engineer | 68 | weeks |  | 0
Site Manager | 68 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 68 | weeks |  | 0
Labourer (including at handover) | 68 | weeks |  | 0
Quantity Surveying / Commercial Management | 68 | weeks |  | 0
Planner | 68 | weeks |  | 0
Health & Safety Officer | 68 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 68 | weeks |  | 0
Meeting room (inc furniture) | 68 | weeks |  | 0
Canteens and Kitchens | 68 | weeks |  | 0
Drying room | 68 | weeks |  | 0
Toilets and washrooms | 68 | weeks |  | 0
Secure stores | 68 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 68 | weeks |  | 0
IT systems with email and internet capability | 68 | weeks |  | 0
Consumables and services associated with site accommodation | 68 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 68 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks |  | 0
Gas Supply | 68 | weeks |  | 0
Electric supply, Lighting and power | 68 | weeks |  | 0
Drainage | 68 | weeks |  | 0
Security
Night watchman | 68 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 68 | weeks |  | 0
Material distribution
Forklift and driver | 34 | weeks |  | 0
Site plant
Small Dumper | 34 | weeks |  | 0
Mixer | 34 | weeks |  | 0
Road Sweeper including driver and fuel | 34 | weeks |  | 0
Excavator / mini digger including driver and fuel | 34 | weeks |  | 0
Small tools and equiptment | 34 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
LOW VALUE LOT L5
TIMBER FRAME CONSTRUCTION
LOCATION | South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks |  | 0
Contracts Manager | 52 | weeks |  | 0
Site Engineer | 52 | weeks |  | 0
Site Manager | 52 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 52 | weeks |  | 0
Labourer (including at handover) | 52 | weeks |  | 0
Quantity Surveying /Commercial Management | 52 | weeks |  | 0
Planner | 52 | weeks |  | 0
Health & Safety Officer | 52 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 52 | weeks |  | 0
Meeting room (inc furniture) | 52 | weeks |  | 0
Canteens and Kitchens | 52 | weeks |  | 0
Drying room | 52 | weeks |  | 0
Toilets and washrooms | 52 | weeks |  | 0
Secure stores | 52 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 52 | weeks |  | 0
IT systems with email and internet capability | 52 | weeks |  | 0
Consumables and services associated with site accommodation | 52 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 52 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks |  | 0
Gas Supply | 52 | weeks |  | 0
Electric supply, Lighting and power | 52 | weeks |  | 0
Drainage | 52 | weeks |  | 0
Security
Night watchman | 52 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 52 | weeks |  | 0
Material distribution
Forklift and driver | 26 | weeks |  | 0
Site plant
Small Dumper | 26 | weeks |  | 0
Mixer | 26 | weeks |  | 0
Road Sweeper including driver and fuel | 26 | weeks |  | 0
Excavator / mini digger including driver and fuel | 26 | weeks |  | 0
Small tools and equiptment | 26 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 8 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 27 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 5 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 5 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 5 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 6 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 6 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 6 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² |  | 0
Preparatory Groundworks | 7942 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² |  | 0
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item |  | 0
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 222500
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 222500
Post Contract Design Fees at say 3% | [5 empty] | 6675
OHP | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 229175
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 229175
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 458350

## High val Lot 1
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | Whitfield & Brown (Developments) Ltd
HIGH VALUE LOT H1 WEST
TRADITIONAL CONSTRUCTION
LOCATION | Greater Manchester, Merseyside, Cheshire, Derbyshire West, Staffordshire, Lancashire, Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 104 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 104 | weeks | 300 | 31200
Contracts Manager | 104 | weeks | 600 | 62400
Site Engineer | 104 | weeks | 50 | 5200
Site Manager | 104 | weeks | 1250 | 130000
Finishing Foreman / Assistant Site Manager | 104 | weeks | 500 | 52000
Labourer (including at handover) | 104 | weeks | 750 | 78000
Quantity Surveying / Commercial Management | 104 | weeks | 600 | 62400
Planner | 104 | weeks | 100 | 10400
Health & Safety Officer | 104 | weeks | 50 | 5200
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 2400 | 2400
Site office (inc furniture) | 104 | weeks | 55 | 5720
Meeting room (inc furniture) | 104 | weeks | 55 | 5720
Canteens and Kitchens | 104 | weeks | 55 | 5720
Drying room | 104 | weeks | 55 | 5720
Toilets and washrooms | 104 | weeks | 55 | 5720
Secure stores | 104 | weeks | 30 | 3120
Telephones and Photocopiers (connection and charges) | 104 | weeks | 50 | 5200
IT systems with email and internet capability | 104 | weeks | 50 | 5200
Consumables and services associated with site accommodation | 104 | weeks | 150 | 15600
Fire points and fire fighting equipment | 1 | Item | 1000 | 1000
Main Contractor's Signboard | 1 | Item | 1000 | 1000
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 1500 | 1500
Cleaning
Site cleaning | 104 | weeks | 80 | 8320
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 104 | weeks | 100 | 10400
Gas Supply | 104 | weeks |  | 0
Electric supply, Lighting and power | 104 | weeks | 150 | 15600
Drainage | 104 | weeks | 20 | 2080
Security
Night watchman | 104 | weeks | 2350 | 244400
Pedestrian gates | 1 | item | 250 | 250
Vehicular gates | 1 | item | 500 | 500
CCTV cameras set up costs | 1 | item | 100 | 100
CCTV weekly charge | 104 | weeks | 350 | 36400
Material distribution
Forklift and driver | 52 | weeks |  | 0 | Included in Works Package
Site plant
Small Dumper | 52 | weeks |  | 0 | Included in Works Package
Mixer | 52 | weeks |  | 0 | Included in Works Package
Road Sweeper including driver and fuel | 52 | weeks |  | 0 | Included in Works Package
Excavator / mini digger including driver and fuel | 52 | weeks |  | 0 | Included in Works Package
Small tools and equiptment | 52 | weeks | 150 | 7800
Health and Safety
1st aid kit | 1 | item | 250 | 250
Health and safety site visits | 1 | item | 2000 | 2000
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0 | Included in Works Package
Adaption of Scaffolding | 1 | item |  | 0 | Included in Works Package
Internal Scaffolding | 1 | item |  | 0 | Included in Works Package
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 250 | 250
CDM regulations and health and safety plan | 1 | item | 250 | 250
Considerate constructors scheme | 1 | item | 1000 | 1000
SAP calculations and energy performance certificates | 1 | item | 2500 | 2500
Robust details | 1 | item | 500 | 500
Building Control Fees | 1 | item | 15000 | 15000
Planning Condition Discharge Fees | 15 | no | 150 | 2250 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 24000 | 24000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 160000 | 160000 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0 | Included in Works Package
Concrete testing and reports | 1 | item |  | 0 | Included in Works Package
Dilapidation Surveys | 1 | Item |  | 0 | Included in Works Package
Sound testing | 1 | item | 2000 | 2000
Air pressure tests | 1 | item | 2500 | 2500
Handover costs
Snagging costs / inspections | 1 | item |  | 0 | Included
Contract cleaners | 1 | item | 15000 | 15000
Clean to external areas | 1 | item |  | 0 | Included
Skips | 15 | no | 200 | 3000
Lorry and tipping charges | 1 | item |  | 0 | Included in Works Package
Resident handover packs | 80 | no | 50 | 4000
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0 | TBA - Job Specific
6.5.1 Insurance | 1 | Item |  | 0 | TBA - Job Specific
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 80 | no |  | 0 | Included
External areas - paths, paving and adopted areas | 1 | item |  | 0 | Included
Landscaped areas | 1 | item |  | 0 | Included
Total of preliminaries |  |  |  | 1062270
Total of preliminaries expressed as a weekly cost |  |  |  | 10214.1346
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 3%
Profit (expressed as a %) |  |  |  | 2%
Overheads and Profit Total |  |  |  | 5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 151 | 10811.6 | 3 | 32434.8
Superstructures
Superstructures | 71.6 | m2 | 1060 | 75896 | 3 | 227688
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 3 | 15000
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 275122.8
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 151 | 10811.6 | 16 | 172985.6
Superstructures
Superstructures | 71.6 | m2 | 1060 | 75896 | 16 | 1214336
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 16 | 80000
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 1467321.6
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 151 | 12865.2 | 7 | 90056.4
Superstructures
Superstructures | 85.2 | m2 | 1060 | 90312 | 7 | 632184
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 7 | 35000
Total cost for 3B4P mid mews houses (NDSS) | [5 empty] | 757240.4
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 151 | 12865.2 | 11 | 141517.2
Superstructures
Superstructures | 85.2 | m2 | 1060 | 90312 | 11 | 993432
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 11 | 55000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1189949.2
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 151 | 13001.1 | 11 | 143012.1
Superstructures
Superstructures | 86.1 | m2 | 1060 | 91266 | 11 | 1003926
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 11 | 55000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1201938.1
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 151 | 14224.2 | 22 | 312932.4
Superstructures
Superstructures | 94.2 | m2 | 1060 | 99852 | 22 | 2196744
Allowance for Part L June 22 uplift | 1 | item | 7500 | 7500 | 22 | 165000
Total cost for 3B5P houses (NDSS) | [5 empty] | 2674676.4
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 | 151 | 16353.3 | 10 | 163533
Superstructures
Superstructures | 108.3 | m2 | 1060 | 114798 | 10 | 1147980
Allowance for Part L June 22 uplift | 1 | item | 7500 | 7500 | 10 | 75000
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 1386513
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² | 10 | 191820
Preparatory Groundworks | 19182 | m² | 1 | 19182
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² | 167.5 | 232657.5
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² | 145.8 | 149007.6
Non Adopted footpath (tarmac) including all edgings | 125 | m² | 125 | 15625
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² | 135 | 468045
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² | 105 | 224070
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² | 25 | 151625
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no | 195 | 16770
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm | 75 | 96150
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm | 95 | 37050
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item | 1500 | 120000
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 2450302.1
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 1062270
Substructure | [5 empty] | 1056471.5
Superstructure | [5 empty] | 7416290
Part L Uplift | [5 empty] | 480000
External Works | [5 empty] | 2450302.1
Post Contract Design Fees at say 3% | [5 empty] | 373960.008
OH&P | [5 empty] | 641964.6804
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 13481258.2884
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | Whitfield & Brown (Developments) Ltd
HIGH VALUE LOT H1 WEST
TIMBER FRAME CONSTRUCTION
LOCATION | Greater Manchester, Merseyside, Cheshire, Derbyshire West, Staffordshire, Lancashire, Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 86 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 86 | weeks | 300 | 25800
Contracts Manager | 86 | weeks | 600 | 51600
Site Engineer | 86 | weeks | 50 | 4300
Site Manager | 86 | weeks | 1250 | 107500
Finishing Foreman / Assistant Site Manager | 86 | weeks | 500 | 43000
Labourer (including at handover) | 86 | weeks | 750 | 64500
Quantity Surveying /Commercial Management | 86 | weeks | 600 | 51600
Planner | 86 | weeks | 100 | 8600
Health & Safety Officer | 86 | weeks | 50 | 4300
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 2400 | 2400
Site office (inc furniture) | 86 | weeks | 55 | 4730
Meeting room (inc furniture) | 86 | weeks | 55 | 4730
Canteens and Kitchens | 86 | weeks | 55 | 4730
Drying room | 86 | weeks | 55 | 4730
Toilets and washrooms | 86 | weeks | 55 | 4730
Secure stores | 86 | weeks | 30 | 2580
Telephones and Photocopiers (connection and charges) | 86 | weeks | 50 | 4300
IT systems with email and internet capability | 86 | weeks | 50 | 4300
Consumables and services associated with site accommodation | 86 | weeks | 150 | 12900
Fire points and fire fighting equipment | 1 | Item | 1000 | 1000
Main Contractor's Signboard | 1 | Item | 1000 | 1000
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 1500 | 1500
Cleaning
Site cleaning | 86 | weeks | 80 | 6880
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0 | **
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0 | **
Temproary fencing to compound area | 1 | item |  | 0 | **
Temporary security fencing to site perimeter | 1 | item |  | 0 | **
Removal of compound on completion; reinstatement | 1 | item |  | 0 | **
Temp Services incl all connections, disconnections and usage
Water supply | 86 | weeks | 100 | 8600
Gas Supply | 86 | weeks |  | 0 | N/A
Electric supply, Lighting and power | 86 | weeks | 150 | 12900
Drainage | 86 | weeks | 20 | 1720
Security
Night watchman | 86 | weeks | 2350 | 202100
Pedestrian gates | 1 | item | 250 | 250
Vehicular gates | 1 | item | 500 | 500
CCTV cameras set up costs | 1 | item | 100 | 100
CCTV weekly charge | 86 | weeks | 350 | 30100
Material distribution
Forklift and driver | 43 | weeks |  | 0 | Included in Works Package
Site plant
Small Dumper | 43 | weeks |  | 0 | Included in Works Package
Mixer | 43 | weeks |  | 0 | Included in Works Package
Road Sweeper including driver and fuel | 43 | weeks |  | 0 | Included in Works Package
Excavator / mini digger including driver and fuel | 43 | weeks |  | 0 | Included in Works Package
Small tools and equiptment | 43 | weeks | 150 | 6450
Health and Safety
1st aid kit | 1 | item | 250 | 250
Health and safety site visits | 1 | item | 2000 | 2000
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 250 | 250
CDM regulations and health and safety plan | 1 | item | 250 | 250
Considerate constructors scheme | 1 | item | 1000 | 1000
SAP calculations and energy performance certificates | 1 | item | 6000 | 6000
Robust details | 1 | item | 500 | 500
Building Control Fees | 1 | item | 14000 | 14000 | ********
Planning Condition Discharge Fees | 1 | item | 150 | 150 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 24000 | 24000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 160000 | 160000 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0 | Included in Works Package
Concrete testing and reports | 1 | item |  | 0 | Included in Works Package
Dilapidation Surveys | 1 | Item |  | 0 | Included in Works Package
Sound testing | 1 | item | 2000 | 2000
Air pressure tests | 1 | item | 2500 | 2500
Handover costs
Snagging costs | 1 | item |  | 0 | Included
Contract cleaners | 1 | item | 15000 | 15000
Clean to external areas | 1 | item |  | 0 | Included
Skips | 15 | no | 200 | 3000
Lorry and tipping charges | 1 | item |  | 0 | Included in Works Package
Resident handover packs | 80 | no | 50 | 4000
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0 | TBA - Job Specific
6.5.1 Insurance | 1 | Item |  | 0 | TBA - Job Specific
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 80 | no |  | 0 | Included
External areas - paths, paving and adopted areas | 1 | item |  | 0 | Included
Landscaped areas | 1 | item |  | 0 | Included
Total of preliminaries |  |  |  | 920830
Total of preliminaries expressed as a weekly cost |  |  |  | 10707.3256
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 3%
Profit (expressed as a %) |  |  |  | 2%
Overheads and Profit Total |  |  |  | 5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 151 | 10811.6 | 3 | 32434.8
Superstructures
Superstructures | 71.6 | m2 | 1118 | 80048.8 | 3 | 240146.4
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 3 | 15000
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 287581.2
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 151 | 10811.6 | 16 | 172985.6
Superstructures
Superstructures | 71.6 | m2 | 1118 | 80048.8 | 16 | 1280780.8
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 16 | 80000
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 1533766.4
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 151 | 12865.2 | 7 | 90056.4
Superstructures
Superstructures | 85.2 | m2 | 1118 | 95253.6 | 7 | 666775.2
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 7 | 35000
Total cost for 3B4P mid mews houses (NDSS) | [5 empty] | 791831.6
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 151 | 12865.2 | 11 | 141517.2
Superstructures
Superstructures | 85.2 | m2 | 1118 | 95253.6 | 11 | 1047789.6
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 11 | 55000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1244306.8
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 151 | 13001.1 | 11 | 143012.1
Superstructures
Superstructures | 86.1 | m2 | 1118 | 96259.8 | 11 | 1058857.8
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 11 | 55000
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1256869.9
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 151 | 14224.2 | 22 | 312932.4
Superstructures
Superstructures | 94.2 | m2 | 1118 | 105315.6 | 22 | 2316943.2
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 22 | 110000
Total cost for 3B5P houses (NDSS) | [5 empty] | 2739875.6
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 | 151 | 16353.3 | 10 | 163533
Superstructures
Superstructures | 108.3 | m2 | 1118 | 121079.4 | 10 | 1210794
Allowance for Part L June 22 uplift | 1 | item | 5000 | 5000 | 10 | 50000
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 1424327
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² | 10 | 191820
Preparatory Groundworks | 19182 | m² | 1 | 19182
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² | 167.5 | 232657.5
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² | 145.8 | 149007.6
Non Adopted footpath (tarmac) including all edgings | 125 | m² | 125 | 15625
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² | 135 | 468045
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² | 105 | 224070
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² | 25 | 151625
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no | 195 | 16770
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm | 75 | 96150
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm | 95 | 37050
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item | 1500 | 120000
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 2450302.1
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 920830
Substructure | [5 empty] | 1056471.5
Superstructure | [5 empty] | 7822087
Part L Uplift | [5 empty] | 400000
External Works | [5 empty] | 2450302.1
Post Contract Design Fees at say 3% | [5 empty] | 379490.718
OH&P | [5 empty] | 651459.0659
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 13680640.3839
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 13481258.2884
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 13680640.3839
TOTAL COMBINED SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 80 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 27161898.6723

## High val Lot 2
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
HIGH VALUE LOT H2 EAST
TRADITIONAL CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham, North Yorkshire, West Yorkshire, East Yorkshire, South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 104 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 104 | weeks |  | 0
Contracts Manager | 104 | weeks |  | 0
Site Engineer | 104 | weeks |  | 0
Site Manager | 104 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 104 | weeks |  | 0
Labourer (including at handover) | 104 | weeks |  | 0
Quantity Surveying / Commercial Management | 104 | weeks |  | 0
Planner | 104 | weeks |  | 0
Health & Safety Officer | 104 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 104 | weeks |  | 0
Meeting room (inc furniture) | 104 | weeks |  | 0
Canteens and Kitchens | 104 | weeks |  | 0
Drying room | 104 | weeks |  | 0
Toilets and washrooms | 104 | weeks |  | 0
Secure stores | 104 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 104 | weeks |  | 0
IT systems with email and internet capability | 104 | weeks |  | 0
Consumables and services associated with site accommodation | 104 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 104 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 104 | weeks |  | 0
Gas Supply | 104 | weeks |  | 0
Electric supply, Lighting and power | 104 | weeks |  | 0
Drainage | 104 | weeks |  | 0
Security
Night watchman | 104 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 104 | weeks |  | 0
Material distribution
Forklift and driver | 52 | weeks |  | 0
Site plant
Small Dumper | 52 | weeks |  | 0
Mixer | 52 | weeks |  | 0
Road Sweeper including driver and fuel | 52 | weeks |  | 0
Excavator / mini digger including driver and fuel | 52 | weeks |  | 0
Small tools and equiptment | 52 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 15 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 80 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 80 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 16 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 16 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 16 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 7 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 7 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 7 | 0
Total cost for 3B4P mid mews houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 22 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 22 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 22 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 108.3 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² |  | 0
Preparatory Groundworks | 19182 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | 125 | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² |  | 0
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item |  | 0
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 728300
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 728300
Post Contract Design Fees at say 3% | [5 empty] | 21849
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 750149
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
HIGH VALUE LOT H2 EAST
TIMBER FRAME CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham, North Yorkshire, West Yorkshire, East Yorkshire, South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 86 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 86 | weeks |  | 0
Contracts Manager | 86 | weeks |  | 0
Site Engineer | 86 | weeks |  | 0
Site Manager | 86 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 86 | weeks |  | 0
Labourer (including at handover) | 86 | weeks |  | 0
Quantity Surveying /Commercial Management | 86 | weeks |  | 0
Planner | 86 | weeks |  | 0
Health & Safety Officer | 86 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 86 | weeks |  | 0
Meeting room (inc furniture) | 86 | weeks |  | 0
Canteens and Kitchens | 86 | weeks |  | 0
Drying room | 86 | weeks |  | 0
Toilets and washrooms | 86 | weeks |  | 0
Secure stores | 86 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 86 | weeks |  | 0
IT systems with email and internet capability | 86 | weeks |  | 0
Consumables and services associated with site accommodation | 86 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 86 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 86 | weeks |  | 0
Gas Supply | 86 | weeks |  | 0
Electric supply, Lighting and power | 86 | weeks |  | 0
Drainage | 86 | weeks |  | 0
Security
Night watchman | 86 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 86 | weeks |  | 0
Material distribution
Forklift and driver | 43 | weeks |  | 0
Site plant
Small Dumper | 43 | weeks |  | 0
Mixer | 43 | weeks |  | 0
Road Sweeper including driver and fuel | 43 | weeks |  | 0
Excavator / mini digger including driver and fuel | 43 | weeks |  | 0
Small tools and equiptment | 43 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 1 | item |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 15 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 80 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 80 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 16 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 16 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 16 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 7 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 7 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 7 | 0
Total cost for 3B4P mid mews houses (Non NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 22 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 22 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 22 | 0
Total cost for 3B5P houses (Non NDSS) | [5 empty] | 0
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 108.3 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² |  | 0
Preparatory Groundworks | 19182 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | 125 | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² |  | 0
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item |  | 0
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 728300
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 728300
Post Contract Design Fees at say 3% | [5 empty] | 21849
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 750149
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 750149
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 750149
TOTAL COMBINED SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 80 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 1500298