## Summary Sheet
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SUMMARY SHEET
TENDERER'S NAME | McCaul Build Ltd
SUMMARY OF TOTAL COMBINED COST FOR TIMBER FRAME AND TRADITIONAL CONSTRUCTION
LOT | COMBINED TOTAL
Low Value L1 | 8849854.1176
Low Value L2 | 8973184.3775
Low Value L3 | 9283014.6183
Low Value L4 | 9065360.3932
Low Value L5 | 9239338.3554
High Value H1 | 1500298
High Value H2 | 1500298
NOTE: Where the 'Combined Total' cells above are highlighted red it is taken that the contractor is not tendering for the lot in question. Only pricing in the green highlighted cells will be taken forward.

## Low val Lot 1
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | McCaul Build Ltd
LOW VALUE LOT L1
TRADITIONAL CONSTRUCTION
LOCATION | Greater Manchester and Merseyside, Cheshire, Derbyshire West and Staffordshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks | 0 | 0
Contracts Manager | 68 | weeks | 200 | 13600
Site Engineer | 68 | weeks | 200 | 13600
Site Manager | 68 | weeks | 950 | 64600
Finishing Foreman / Assistant Site Manager | 68 | weeks | 500 | 34000
Labourer (including at handover) | 68 | weeks | 200 | 13600
Quantity Surveying / Commercial Management | 68 | weeks | 200 | 13600
Planner | 68 | weeks | 0 | 0
Health & Safety Officer | 68 | weeks | 0 | 0 | Included in Health and Safety Site Visits
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 1800 | 1800
Site office (inc furniture) | 68 | weeks | 37.35 | 2539.8
Meeting room (inc furniture) | 68 | weeks | 37.35 | 2539.8
Canteens and Kitchens | 68 | weeks | 36.75 | 2499
Drying room | 68 | weeks | 36.75 | 2499
Toilets and washrooms | 68 | weeks | 91 | 6188
Secure stores | 68 | weeks | 15 | 1020
Telephones and Photocopiers (connection and charges) | 68 | weeks | 5 | 340
IT systems with email and internet capability | 68 | weeks | 10 | 680
Consumables and services associated with site accommodation | 68 | weeks | 50 | 3400
Fire points and fire fighting equipment | 1 | Item | 1400 | 1400
Main Contractor's Signboard | 1 | Item | 480 | 480
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 997.5 | 997.5
Cleaning
Site cleaning | 68 | weeks | 80 | 5440
Site set up
Tarmac and hardcore compound area | 1 | item | 0 | 0 | Compound constructed as permanent finish, therefore no additional cost
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item | 1400 | 1400
Temproary fencing to compound area | 1 | item | 600 | 600
Temporary security fencing to site perimeter | 1 | item | 4000 | 4000
Removal of compound on completion; reinstatement | 1 | item | 0 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks | 55 | 3740
Gas Supply | 68 | weeks | 15 | 1020
Electric supply, Lighting and power | 68 | weeks | 125 | 8500
Drainage | 68 | weeks | 25 | 1700
Security
Night watchman | 68 | weeks | 1305 | 88740 | 75% of Programme
Pedestrian gates | 1 | item | 120 | 120
Vehicular gates | 1 | item | 240 | 240
CCTV cameras set up costs | 1 | item | 200 | 200
CCTV weekly charge | 68 | weeks | 175 | 11900
Material distribution
Forklift and driver | 34 | weeks | 1000 | 34000
Site plant
Small Dumper | 34 | weeks | 0 | 0 | Included in Groundworks rates
Mixer | 34 | weeks | 0 | 0 | Included in Small Tools and Equipment Sum
Road Sweeper including driver and fuel | 34 | weeks | 90 | 3060 | Allow 1nr per week (as an average)
Excavator / mini digger including driver and fuel | 34 | weeks | 0 | 0 | Included in Groundworks rates
Small tools and equiptment | 34 | weeks | 300 | 10200
Health and Safety
1st aid kit | 1 | item | 49.99 | 49.99
Health and safety site visits | 1 | item | 4000 | 4000
Falling from heights | 1 | item | 0 | 0 | Included in Relevant Packages
Scaffolding
External scaffolding including mat | 1 | item | 78229 | 78229
Adaption of Scaffolding | 1 | item | 0 | 0 | Included above
Internal Scaffolding | 1 | item | 0 | 0 | Included above
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 3000 | 3000
CDM regulations and health and safety plan | 1 | item | 500 | 500
Considerate constructors scheme | 1 | item | 300 | 300
SAP calculations and energy performance certificates | 1 | item | 1215 | 1215
Robust details | 1 | item | 1012.5 | 1012.5
Building Control Fees | 1 | item | 7582.8 | 7582.8
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 10000 | 10000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 98683.92 | 98683.92 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0
Concrete testing and reports | 1 | item | 832 | 832
Dilapidation Surveys | 1 | Item | 450 | 450
Sound testing | 1 | item | 0 | 0 | Robust Details Included
Air pressure tests | 1 | item | 900 | 900
Handover costs
Snagging costs / inspections | 1 | item | 0 | 0
Contract cleaners | 1 | item | 5940 | 5940
Clean to external areas | 1 | item | 500 | 500
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item | 0 | 0 | Included above
Resident handover packs | 27 | no | 5 | 135
Insurances and Guarantees
Project specific Insurances | 1 | Item | 8000 | 8000
6.5.1 Insurance | 1 | Item |  | 0 | Included in Overheads
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no | 200 | 5400
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | Covered by retention
Landscaped areas | 1 | item | 0 | 0 | Covered by retention
Total of preliminaries |  |  |  | 585573.31
Total of preliminaries expressed as a weekly cost |  |  |  | 8611.3722
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4%
Profit (expressed as a %) |  |  |  | 4.5%
Overheads and Profit Total |  |  |  | 8.5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 203.6 | 14577.76 | 3 | 43733.28
Superstructures
Superstructures | 71.6 | m2 | 911.71 | 65278.436 | 3 | 195835.308
Allowance for Part L June 22 uplift | 1 | item | 3749.38 | 3749.38 | 3 | 11248.14
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 250816.728
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 216.93 | 15532.188 | 5 | 77660.94
Superstructures
Superstructures | 71.6 | m2 | 978.44 | 70056.304 | 5 | 350281.52
Allowance for Part L June 22 uplift | 1 | item | 3714.82 | 3714.82 | 5 | 18574.1
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 446516.56
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 205.05 | 17470.26 | 10 | 174702.6
Superstructures
Superstructures | 85.2 | m2 | 893.43 | 76120.236 | 10 | 761202.36
Allowance for Part L June 22 uplift | 1 | item | 3880.7 | 3880.7 | 10 | 38807
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 974711.96
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 206.95 | 17818.395 | 3 | 53455.185
Superstructures
Superstructures | 86.1 | m2 | 880.81 | 75837.741 | 3 | 227513.223
Allowance for Part L June 22 uplift | 1 | item | 3880.7 | 3880.7 | 3 | 11642.1
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 292610.508
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 199.97 | 18837.174 | 6 | 113023.044
Superstructures
Superstructures | 94.2 | m2 | 849.34 | 80007.828 | 6 | 480046.968
Allowance for Part L June 22 uplift | 1 | item | 3963.63 | 3963.63 | 6 | 23781.78
Total cost for 3B5P houses (NDSS) | [5 empty] | 616851.792
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 10.58 | 84026.36
Preparatory Groundworks | 7942 | m² | 0.5425 | 4308.535
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 106.01 | 86292.14
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 85.35 | 50527.2
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 97.07 | 87363
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 75.95 | 93038.75
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 27.13 | 71596.07
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 200.73 | 5821.17
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 86.8 | 44007.6
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 91.14 | 36547.14
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 2170 | 58590
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 844617.965
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 585573.31
Substructure | [5 empty] | 462575.049
Superstructure | [5 empty] | 2014879.379
Part L Uplift | [5 empty] | 104053.12
External Works | [5 empty] | 844617.965
Post Contract Design Fees at say 3% | [5 empty] | 120350.9647
OH&P | [5 empty] | 351224.232
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4483274.0196
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | McCaul Build Ltd
LOW VALUE LOT L1
TIMBER FRAME CONSTRUCTION
LOCATION | Greater Manchester and Merseyside, Cheshire, Derbyshire West and Staffordshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks | 0 | 0
Contracts Manager | 52 | weeks | 200 | 10400
Site Engineer | 52 | weeks | 200 | 10400
Site Manager | 52 | weeks | 950 | 49400
Finishing Foreman / Assistant Site Manager | 52 | weeks | 500 | 26000
Labourer (including at handover) | 52 | weeks | 200 | 10400
Quantity Surveying /Commercial Management | 52 | weeks | 200 | 10400
Planner | 52 | weeks | 0 | 0
Health & Safety Officer | 52 | weeks | 0 | 0 | Included in Health and Safety Site Visits
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 1800 | 1800
Site office (inc furniture) | 52 | weeks | 37.35 | 1942.2
Meeting room (inc furniture) | 52 | weeks | 37.35 | 1942.2
Canteens and Kitchens | 52 | weeks | 36.75 | 1911
Drying room | 52 | weeks | 36.75 | 1911
Toilets and washrooms | 52 | weeks | 91 | 4732
Secure stores | 52 | weeks | 15 | 780
Telephones and Photocopiers (connection and charges) | 52 | weeks | 5 | 260
IT systems with email and internet capability | 52 | weeks | 10 | 520
Consumables and services associated with site accommodation | 52 | weeks | 50 | 2600
Fire points and fire fighting equipment | 1 | Item | 1400 | 1400
Main Contractor's Signboard | 1 | Item | 480 | 480
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 997.5 | 997.5
Cleaning
Site cleaning | 52 | weeks | 80 | 4160
Site set up
Tarmac and hardcored compound area | 1 | item | 0 | 0 | Compound constructed as permanent finish, therefore no additional cost
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item | 1400 | 1400
Temproary fencing to compound area | 1 | item | 600 | 600
Temporary security fencing to site perimeter | 1 | item | 4000 | 4000
Removal of compound on completion; reinstatement | 1 | item | 0 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks | 55 | 2860
Gas Supply | 52 | weeks | 15 | 780
Electric supply, Lighting and power | 52 | weeks | 125 | 6500
Drainage | 52 | weeks | 25 | 1300
Security
Night watchman | 52 | weeks | 1305 | 67860 | 75% of Programme
Pedestrian gates | 1 | item | 120 | 120
Vehicular gates | 1 | item | 240 | 240
CCTV cameras set up costs | 1 | item | 200 | 200
CCTV weekly charge | 52 | weeks | 175 | 9100
Material distribution
Forklift and driver | 26 | weeks | 1000 | 26000
Site plant
Small Dumper | 26 | weeks | 0 | 0 | Included in Groundworks rates
Mixer | 26 | weeks | 0 | 0 | Included in Small Tools and Equipment Sum
Road Sweeper including driver and fuel | 26 | weeks | 90 | 2340 | Allow 1nr per week (as an average)
Excavator / mini digger including driver and fuel | 26 | weeks | 0 | 0 | Included in Groundworks rates
Small tools and equiptment | 26 | weeks | 300 | 7800
Health and Safety
1st aid kit | 1 | item | 49.99 | 49.99
Health and safety site visits | 1 | item | 3200 | 3200
Falling from heights | 1 | item | 0 | 0 | Included in Relevant Packages
Scaffolding
External scaffolding including mat | 1 | item | 96618 | 96618
Adaption of Scaffolding | 1 | item | 0 | 0 | Included above
Internal Scaffolding | 1 | item | 0 | 0 | Included above
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 3000 | 3000
CDM regulations and health and safety plan | 1 | item | 500 | 500
Considerate constructors scheme | 1 | item | 300 | 300
SAP calculations and energy performance certificates | 1 | item | 1215 | 1215
Robust details | 1 | item | 1012.5 | 1012.5
Building Control Fees | 1 | item | 7582.8 | 7582.8
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 10000 | 10000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 98683.92 | 98683.92 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0
Concrete testing and reports | 1 | item | 832 | 832
Dilapidation Surveys | 1 | Item | 450 | 450
Sound testing | 1 | item | 0 | 0 | Robust Details Included
Air pressure tests | 1 | item | 900 | 900
Handover costs
Snagging costs | 1 | item | 0 | 0
Contract cleaners | 1 | item | 5940 | 5940
Clean to external areas | 1 | item | 500 | 500
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item | 0 | 0 | Included above
Resident handover packs | 27 | no | 5 | 135
Insurances and Guarantees
Project specific Insurance | 1 | Item | 8000 | 8000
6.5.1 Insurance | 1 | Item |  | 0 | Included in Overheads
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no | 200 | 5400
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | Covered by retention
Landscaped areas | 1 | item | 0 | 0 | Covered by retention
Total of preliminaries |  |  |  | 522455.11
Total of preliminaries expressed as a weekly cost |  |  |  | 10047.2137
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4%
Profit (expressed as a %) |  |  |  | 4.5%
Overheads and Profit Total |  |  |  | 8.5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 203.6 | 14577.76 | 3 | 43733.28
Superstructures
Superstructures | 71.6 | m2 | 863.79 | 61847.364 | 3 | 185542.092
Allowance for Part L June 22 uplift | 1 | item | 3749.38 | 3749.38 | 3 | 11248.14
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 240523.512
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 216.93 | 15532.188 | 5 | 77660.94
Superstructures
Superstructures | 71.6 | m2 | 953.53 | 68272.748 | 5 | 341363.74
Allowance for Part L June 22 uplift | 1 | item | 3714.82 | 3714.82 | 5 | 18574.1
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 437598.78
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 205.05 | 17470.26 | 10 | 174702.6
Superstructures
Superstructures | 85.2 | m2 | 880.91 | 75053.532 | 10 | 750535.32
Allowance for Part L June 22 uplift | 1 | item | 3880.7 | 3880.7 | 10 | 38807
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 964044.92
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 206.95 | 17818.395 | 3 | 53455.185
Superstructures
Superstructures | 86.1 | m2 | 871.77 | 75059.397 | 3 | 225178.191
Allowance for Part L June 22 uplift | 1 | item | 3880.7 | 3880.7 | 3 | 11642.1
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 290275.476
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 199.97 | 18837.174 | 6 | 113023.044
Superstructures
Superstructures | 94.2 | m2 | 833.31 | 78497.802 | 6 | 470986.812
Allowance for Part L June 22 uplift | 1 | item | 3963.63 | 3963.63 | 6 | 23781.78
Total cost for 3B5P houses (NDSS) | [5 empty] | 607791.636
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 10.58 | 84026.36
Preparatory Groundworks | 7942 | m² | 0.54 | 4288.68
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 106 | 86284
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 85.35 | 50527.2
Non Adopted footpath (tarmac) including all edgings | nil | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 97.07 | 87363
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 75.95 | 93038.75
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 27.13 | 71596.07
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 200.73 | 5821.17
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 86.8 | 44007.6
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 91.14 | 36547.14
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 2170 | 58590
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 844589.97
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 522455.11
Substructure | [5 empty] | 462575.049
Superstructure | [5 empty] | 1973606.155
Part L Uplift | [5 empty] | 104053.12
External Works | [5 empty] | 844589.97
Post Contract Design Fees at say 3% | [5 empty] | 117218.3821
OHP | [5 empty] | 342082.3118
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4366580.0979
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4483274.0196
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4366580.0979
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 8849854.1176

## Low val Lot 2
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | McCaul Build Ltd
LOW VALUE LOT L2
TRADITIONAL CONSTRUCTION
LOCATION | Lancashire and Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks | 0 | 0
Contracts Manager | 68 | weeks | 200 | 13600
Site Engineer | 68 | weeks | 200 | 13600
Site Manager | 68 | weeks | 950 | 64600
Finishing Foreman / Assistant Site Manager | 68 | weeks | 500 | 34000
Labourer (including at handover) | 68 | weeks | 200 | 13600
Quantity Surveying / Commercial Management | 68 | weeks | 200 | 13600
Planner | 68 | weeks | 0 | 0
Health & Safety Officer | 68 | weeks | 0 | 0 | Included in Health and Safety Site Visits
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 1800 | 1800
Site office (inc furniture) | 68 | weeks | 37.35 | 2539.8
Meeting room (inc furniture) | 68 | weeks | 37.35 | 2539.8
Canteens and Kitchens | 68 | weeks | 36.75 | 2499
Drying room | 68 | weeks | 36.75 | 2499
Toilets and washrooms | 68 | weeks | 91 | 6188
Secure stores | 68 | weeks | 15 | 1020
Telephones and Photocopiers (connection and charges) | 68 | weeks | 5 | 340
IT systems with email and internet capability | 68 | weeks | 10 | 680
Consumables and services associated with site accommodation | 68 | weeks | 50 | 3400
Fire points and fire fighting equipment | 1 | Item | 1400 | 1400
Main Contractor's Signboard | 1 | Item | 480 | 480
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 997.5 | 997.5
Cleaning
Site cleaning | 68 | weeks | 80 | 5440
Site set up
Tarmac and hardcore compound area | 1 | item | 0 | 0 | Compound constructed as permanent finish, therefore no additional cost
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item | 1400 | 1400
Temproary fencing to compound area | 1 | item | 600 | 600
Temporary security fencing to site perimeter | 1 | item | 4000 | 4000
Removal of compound on completion; reinstatement | 1 | item | 0 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks | 55 | 3740
Gas Supply | 68 | weeks | 15 | 1020
Electric supply, Lighting and power | 68 | weeks | 125 | 8500
Drainage | 68 | weeks | 25 | 1700
Security
Night watchman | 68 | weeks | 1305 | 88740 | 75% of programme
Pedestrian gates | 1 | item | 120 | 120
Vehicular gates | 1 | item | 240 | 240
CCTV cameras set up costs | 1 | item | 200 | 200
CCTV weekly charge | 68 | weeks | 175 | 11900
Material distribution
Forklift and driver | 34 | weeks | 1000 | 34000
Site plant
Small Dumper | 34 | weeks | 0 | 0 | Included in Groundworks rates
Mixer | 34 | weeks | 0 | 0 | Included in Small Tools and Equipment Sum
Road Sweeper including driver and fuel | 34 | weeks | 90 | 3060 | Allow 1nr per week (as an average)
Excavator / mini digger including driver and fuel | 34 | weeks | 0 | 0 | Included in Groundworks rates
Small tools and equiptment | 34 | weeks | 300 | 10200
Health and Safety
1st aid kit | 1 | item | 49.99 | 49.99
Health and safety site visits | 1 | item | 4000 | 4000
Falling from heights | 1 | item | 0 | 0 | Included in Relevant Packages
Scaffolding
External scaffolding including mat | 1 | item | 78229 | 78229
Adaption of Scaffolding | 1 | item | 0 | 0 | Included above
Internal Scaffolding | 1 | item | 0 | 0 | Included above
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 3000 | 3000
CDM regulations and health and safety plan | 1 | item | 500 | 500
Considerate constructors scheme | 1 | item | 300 | 300
SAP calculations and energy performance certificates | 1 | item | 1215 | 1215
Robust details | 1 | item | 1012.5 | 1012.5
Building Control Fees | 1 | item | 7582.8 | 7582.8
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 10000 | 10000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 98683.92 | 98683.92 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0
Concrete testing and reports | 1 | item | 832 | 832
Dilapidation Surveys | 1 | Item | 450 | 450
Sound testing | 1 | item | 0 | 0 | Robust Details Included
Air pressure tests | 1 | item | 900 | 900
Handover costs
Snagging costs / inspections | 1 | item | 0 | 0
Contract cleaners | 1 | item | 5940 | 5940
Clean to external areas | 1 | item | 500 | 500
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item | 0 | 0 | Included above
Resident handover packs | 27 | no | 5 | 135
Insurances and Guarantees
Project specific Insurances | 1 | Item | 8000 | 8000
6.5.1 Insurance | 1 | Item | 0 | 0 | Included in Overheads
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no | 200 | 5400
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | Covered by retention
Landscaped areas | 1 | item | 0 | 0 | Covered by retention
Total of preliminaries |  |  |  | 585573.31
Total of preliminaries expressed as a weekly cost |  |  |  | 8611.3722
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4%
Profit (expressed as a %) |  |  |  | 4.5%
Overheads and Profit Total |  |  |  | 8.5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 206.41 | 14778.956 | 3 | 44336.868
Superstructures
Superstructures | 71.6 | m2 | 929.41 | 66545.756 | 3 | 199637.268
Allowance for Part L June 22 uplift | 1 | item | 3822.18 | 3822.18 | 3 | 11466.54
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 255440.676
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 219.93 | 15746.988 | 5 | 78734.94
Superstructures
Superstructures | 71.6 | m2 | 997.44 | 71416.704 | 5 | 357083.52
Allowance for Part L June 22 uplift | 1 | item | 3786.96 | 3786.96 | 5 | 18934.8
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 454753.26
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 207.88 | 17711.376 | 10 | 177113.76
Superstructures
Superstructures | 85.2 | m2 | 910.78 | 77598.456 | 10 | 775984.56
Allowance for Part L June 22 uplift | 1 | item | 3956.05 | 3956.05 | 10 | 39560.5
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 992658.82
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 209.81 | 18064.641 | 3 | 54193.923
Superstructures
Superstructures | 86.1 | m2 | 897.91 | 77310.051 | 3 | 231930.153
Allowance for Part L June 22 uplift | 1 | item | 3596.05 | 3596.05 | 3 | 10788.15
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 296912.226
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 202.74 | 19098.108 | 6 | 114588.648
Superstructures
Superstructures | 94.2 | m2 | 865.84 | 81562.128 | 6 | 489372.768
Allowance for Part L June 22 uplift | 1 | item | 4040.59 | 4040.59 | 6 | 24243.54
Total cost for 3B5P houses (NDSS) | [5 empty] | 628204.956
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 10.72 | 85138.24
Preparatory Groundworks | 7942 | m² | 0.55 | 4368.1
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 107.47 | 87480.58
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 86.52 | 51219.84
Non Adopted footpath (tarmac) including all edgings | nil | m² | 0 | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 98.41 | 88569
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 77 | 94325
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 27.5 | 72572.5
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 203.5 | 5901.5
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 88 | 44616
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 92.4 | 37052.4
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 2200 | 59400
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 853143.16
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 585573.31
Substructure | [5 empty] | 468968.139
Superstructure | [5 empty] | 2054008.269
Part L Uplift | [5 empty] | 104993.53
External Works | [5 empty] | 853143.16
Post Contract Design Fees at say 3% | [5 empty] | 122000.5922
OH&P | [5 empty] | 356038.395
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4544725.3953
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | McCaul Build Ltd
LOW VALUE LOT L2
TIMBER FRAME CONSTRUCTION
LOCATION | Lancashire and Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks | 0 | 0
Contracts Manager | 52 | weeks | 200 | 10400
Site Engineer | 52 | weeks | 200 | 10400
Site Manager | 52 | weeks | 950 | 49400
Finishing Foreman / Assistant Site Manager | 52 | weeks | 500 | 26000
Labourer (including at handover) | 52 | weeks | 200 | 10400
Quantity Surveying /Commercial Management | 52 | weeks | 200 | 10400
Planner | 52 | weeks | 0 | 0
Health & Safety Officer | 52 | weeks | 0 | 0 | Included in Health and Safety Site Visits
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 1800 | 1800
Site office (inc furniture) | 52 | weeks | 37.35 | 1942.2
Meeting room (inc furniture) | 52 | weeks | 37.35 | 1942.2
Canteens and Kitchens | 52 | weeks | 36.75 | 1911
Drying room | 52 | weeks | 36.75 | 1911
Toilets and washrooms | 52 | weeks | 91 | 4732
Secure stores | 52 | weeks | 15 | 780
Telephones and Photocopiers (connection and charges) | 52 | weeks | 5 | 260
IT systems with email and internet capability | 52 | weeks | 10 | 520
Consumables and services associated with site accommodation | 52 | weeks | 50 | 2600
Fire points and fire fighting equipment | 1 | Item | 1400 | 1400
Main Contractor's Signboard | 1 | Item | 480 | 480
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 997.5 | 997.5
Cleaning
Site cleaning | 52 | weeks | 80 | 4160
Site set up
Tarmac and hardcored compound area | 1 | item | 0 | 0 | Compound constructed as permanent finish, therefore no additional cost
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item | 1400 | 1400
Temproary fencing to compound area | 1 | item | 600 | 600
Temporary security fencing to site perimeter | 1 | item | 4000 | 4000
Removal of compound on completion; reinstatement | 1 | item | 0 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks | 55 | 2860
Gas Supply | 52 | weeks | 15 | 780
Electric supply, Lighting and power | 52 | weeks | 125 | 6500
Drainage | 52 | weeks | 25 | 1300
Security
Night watchman | 52 | weeks | 1305 | 67860 | 75% of Programme
Pedestrian gates | 1 | item | 120 | 120
Vehicular gates | 1 | item | 240 | 240
CCTV cameras set up costs | 1 | item | 200 | 200
CCTV weekly charge | 52 | weeks | 175 | 9100
Material distribution
Forklift and driver | 26 | weeks | 1000 | 26000
Site plant
Small Dumper | 26 | weeks | 0 | 0 | Included in Groundworks rates
Mixer | 26 | weeks | 0 | 0 | Included in Small Tools and Equipment Sum
Road Sweeper including driver and fuel | 26 | weeks | 90 | 2340 | Allow 1nr per week (as an average)
Excavator / mini digger including driver and fuel | 26 | weeks | 0 | 0 | Included in Groundworks rates
Small tools and equiptment | 26 | weeks | 300 | 7800
Health and Safety
1st aid kit | 1 | item | 49.99 | 49.99
Health and safety site visits | 1 | item | 3200 | 3200
Falling from heights | 1 | item | 0 | 0 | Included in Relevant Packages
Scaffolding
External scaffolding including mat | 1 | item | 96618 | 96618
Adaption of Scaffolding | 1 | item | 0 | 0 | Included above
Internal Scaffolding | 1 | item | 0 | 0 | Included above
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 3000 | 3000
CDM regulations and health and safety plan | 1 | item | 500 | 500
Considerate constructors scheme | 1 | item | 300 | 300
SAP calculations and energy performance certificates | 1 | item | 1215 | 1215
Robust details | 1 | item | 1012.5 | 1012.5
Building Control Fees | 1 | item | 7582.8 | 7582.8
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 10000 | 10000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 98683.92 | 98683.92 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0
Concrete testing and reports | 1 | item | 832 | 832
Dilapidation Surveys | 1 | Item | 450 | 450
Sound testing | 1 | item | 0 | 0 | Robust Details Included
Air pressure tests | 1 | item | 900 | 900
Handover costs
Snagging costs | 1 | item | 0 | 0
Contract cleaners | 1 | item | 5940 | 5940
Clean to external areas | 1 | item | 500 | 500
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item | 0 | 0 | Included above
Resident handover packs | 27 | no | 5 | 135
Insurances and Guarantees
Project specific Insurance | 1 | Item | 8000 | 8000
6.5.1 Insurance | 1 | Item | 0 | 0 | Included in Overheads
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no | 200 | 5400
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | Covered by retention
Landscaped areas | 1 | item | 0 | 0 | Covered by retention
Total of preliminaries |  |  |  | 522455.11
Total of preliminaries expressed as a weekly cost |  |  |  | 10047.2137
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4%
Profit (expressed as a %) |  |  |  | 4.5%
Overheads and Profit Total |  |  |  | 8.5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 206.41 | 14778.956 | 3 | 44336.868
Superstructures
Superstructures | 71.6 | m2 | 880.57 | 63048.812 | 3 | 189146.436
Allowance for Part L June 22 uplift | 1 | item | 3822.18 | 3822.18 | 3 | 11466.54
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 244949.844
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 219.93 | 15746.988 | 5 | 78734.94
Superstructures
Superstructures | 71.6 | m2 | 972.04 | 69598.064 | 5 | 347990.32
Allowance for Part L June 22 uplift | 1 | item | 3786.96 | 3786.96 | 5 | 18934.8
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 445660.06
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 207.88 | 17711.376 | 10 | 177113.76
Superstructures
Superstructures | 85.2 | m2 | 898.02 | 76511.304 | 10 | 765113.04
Allowance for Part L June 22 uplift | 1 | item | 3956.05 | 3956.05 | 10 | 39560.5
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 981787.3
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 209.81 | 18064.641 | 3 | 54193.923
Superstructures
Superstructures | 86.1 | m2 | 888.69 | 76516.209 | 3 | 229548.627
Allowance for Part L June 22 uplift | 1 | item | 3956.05 | 3956.05 | 3 | 11868.15
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 295610.7
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 202.74 | 19098.108 | 6 | 114588.648
Superstructures
Superstructures | 94.2 | m2 | 849.49 | 80021.958 | 6 | 480131.748
Allowance for Part L June 22 uplift | 1 | item | 4040.59 | 4040.59 | 6 | 24243.54
Total cost for 3B5P houses (NDSS) | [5 empty] | 618963.936
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 10.73 | 85217.66
Preparatory Groundworks | 7942 | m² | 0.55 | 4368.1
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 107.47 | 87480.58
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 86.52 | 51219.84
Non Adopted footpath (tarmac) including all edgings | nil | m² | 0 | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 98.41 | 88569
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 77 | 94325
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 27.5 | 72572.5
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 203.5 | 5901.5
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 88 | 44616
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 92.4 | 37052.4
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 2200 | 59400
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 853222.58
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 522455.11
Substructure | [5 empty] | 468968.139
Superstructure | [5 empty] | 2011930.171
Part L Uplift | [5 empty] | 106073.53
External Works | [5 empty] | 853222.58
Post Contract Design Fees at say 3% | [5 empty] | 118879.4859
OHP | [5 empty] | 346929.9664
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4428458.9823
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4544725.3953
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4428458.9823
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 8973184.3775

## Low val Lot 3
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | McCaul Build Ltd
LOW VALUE LOT L3
TRADITIONAL CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks | 0 | 0
Contracts Manager | 68 | weeks | 200 | 13600
Site Engineer | 68 | weeks | 200 | 13600
Site Manager | 68 | weeks | 950 | 64600
Finishing Foreman / Assistant Site Manager | 68 | weeks | 500 | 34000
Labourer (including at handover) | 68 | weeks | 200 | 13600
Quantity Surveying / Commercial Management | 68 | weeks | 200 | 13600
Planner | 68 | weeks | 0 | 0
Health & Safety Officer | 68 | weeks | 0 | 0 | Included in Health and Safety Site Visits
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 1800 | 1800
Site office (inc furniture) | 68 | weeks | 37.35 | 2539.8
Meeting room (inc furniture) | 68 | weeks | 37.35 | 2539.8
Canteens and Kitchens | 68 | weeks | 36.75 | 2499
Drying room | 68 | weeks | 36.75 | 2499
Toilets and washrooms | 68 | weeks | 91 | 6188
Secure stores | 68 | weeks | 15 | 1020
Telephones and Photocopiers (connection and charges) | 68 | weeks | 5 | 340
IT systems with email and internet capability | 68 | weeks | 10 | 680
Consumables and services associated with site accommodation | 68 | weeks | 50 | 3400
Fire points and fire fighting equipment | 1 | Item | 1400 | 1400
Main Contractor's Signboard | 1 | Item | 480 | 480
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 997.5 | 997.5
Cleaning
Site cleaning | 68 | weeks | 80 | 5440
Site set up
Tarmac and hardcore compound area | 1 | item | 0 | 0 | Compound constructed as permanent finish, therefore no additional cost
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item | 1400 | 1400
Temproary fencing to compound area | 1 | item | 600 | 600
Temporary security fencing to site perimeter | 1 | item | 4000 | 4000
Removal of compound on completion; reinstatement | 1 | item | 0 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks | 55 | 3740
Gas Supply | 68 | weeks | 15 | 1020
Electric supply, Lighting and power | 68 | weeks | 125 | 8500
Drainage | 68 | weeks | 25 | 1700
Security
Night watchman | 68 | weeks | 1305 | 88740 | 75% of Programme
Pedestrian gates | 1 | item | 120 | 120
Vehicular gates | 1 | item | 240 | 240
CCTV cameras set up costs | 1 | item | 200 | 200
CCTV weekly charge | 68 | weeks | 175 | 11900
Material distribution
Forklift and driver | 34 | weeks | 1000 | 34000
Site plant
Small Dumper | 34 | weeks | 0 | 0 | Included in Groundworks rates
Mixer | 34 | weeks | 0 | 0 | Included in Small Tools and Equipment Sum
Road Sweeper including driver and fuel | 34 | weeks | 90 | 3060 | Allow 1nr per week (as an average)
Excavator / mini digger including driver and fuel | 34 | weeks | 0 | 0 | Included in Groundworks rates
Small tools and equiptment | 34 | weeks | 300 | 10200
Health and Safety
1st aid kit | 1 | item | 49.99 | 49.99
Health and safety site visits | 1 | item | 4000 | 4000
Falling from heights | 1 | item | 0 | 0 | Included in Relevant Packages
Scaffolding
External scaffolding including mat | 1 | item | 78229 | 78229
Adaption of Scaffolding | 1 | item | 0 | 0 | Included above
Internal Scaffolding | 1 | item | 0 | 0 | Included above
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 3000 | 3000
CDM regulations and health and safety plan | 1 | item | 500 | 500
Considerate constructors scheme | 1 | item | 300 | 300
SAP calculations and energy performance certificates | 1 | item | 1215 | 1215
Robust details | 1 | item | 1012.5 | 1012.5
Building Control Fees | 1 | item | 7582.8 | 7582.8
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 10000 | 10000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 98683.92 | 98683.92 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0
Concrete testing and reports | 1 | item | 832 | 832
Dilapidation Surveys | 1 | Item | 450 | 450
Sound testing | 1 | item | 0 | 0 | Robust Details Included
Air pressure tests | 1 | item | 900 | 900
Handover costs
Snagging costs / inspections | 1 | item | 0 | 0
Contract cleaners | 1 | item | 5940 | 5940
Clean to external areas | 1 | item | 500 | 500
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item | 0 | 0 | Included above
Resident handover packs | 27 | no | 5 | 135
Insurances and Guarantees
Project specific Insurances | 1 | Item | 8000 | 8000
6.5.1 Insurance | 1 | Item | 0 | 0 | Included in overheads
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no | 200 | 5400
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | Covered by retention
Landscaped areas | 1 | item | 0 | 0 | Covered by retention
Total of preliminaries |  |  |  | 585573.31
Total of preliminaries expressed as a weekly cost |  |  |  | 8611.3722
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4.5%
Profit (expressed as a %) |  |  |  | 5.5%
Overheads and Profit Total |  |  |  | 10%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 206.41 | 14778.956 | 3 | 44336.868
Superstructures
Superstructures | 71.6 | m2 | 964.82 | 69081.112 | 3 | 207243.336
Allowance for Part L June 22 uplift | 1 | item | 3967.79 | 3967.79 | 3 | 11903.37
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 263483.574
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 219.93 | 15746.988 | 5 | 78734.94
Superstructures
Superstructures | 71.6 | m2 | 1035.44 | 74137.504 | 5 | 370687.52
Allowance for Part L June 22 uplift | 1 | item | 3931.22 | 3931.22 | 5 | 19656.1
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 469078.56
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 207.88 | 17711.376 | 10 | 177113.76
Superstructures
Superstructures | 85.2 | m2 | 945.47 | 80554.044 | 10 | 805540.44
Allowance for Part L June 22 uplift | 1 | item | 4106.76 | 4106.76 | 10 | 41067.6
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1023721.8
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 209.81 | 18064.641 | 3 | 54193.923
Superstructures
Superstructures | 86.1 | m2 | 932.12 | 80255.532 | 3 | 240766.596
Allowance for Part L June 22 uplift | 1 | item | 4106.76 | 4106.76 | 3 | 12320.28
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 307280.799
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 202.74 | 19098.108 | 6 | 114588.648
Superstructures
Superstructures | 94.2 | m2 | 898.82 | 84668.844 | 6 | 508013.064
Allowance for Part L June 22 uplift | 1 | item | 4194.52 | 4194.52 | 6 | 25167.12
Total cost for 3B5P houses (NDSS) | [5 empty] | 647768.832
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 10.72 | 85138.24
Preparatory Groundworks | 7942 | m² | 0.55 | 4368.1
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 107.47 | 87480.58
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 86.52 | 51219.84
Non Adopted footpath (tarmac) including all edgings | nil | m² | 0 | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 98.41 | 88569
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 77 | 94325
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 27.5 | 72572.5
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 203.5 | 5901.5
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 88 | 44616
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 92.4 | 37052.4
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 2200 | 59400
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 853143.16
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 585573.31
Substructure | [5 empty] | 468968.139
Superstructure | [5 empty] | 2132250.956
Part L Uplift | [5 empty] | 110114.47
External Works | [5 empty] | 853143.16
Post Contract Design Fees at say 3% | [5 empty] | 124501.5011
OH&P | [5 empty] | 427455.1536
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4702006.6897
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | McCaul Build Ltd
LOW VALUE LOT L3
TIMBER FRAME CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks | 0 | 0
Contracts Manager | 52 | weeks | 200 | 10400
Site Engineer | 52 | weeks | 200 | 10400
Site Manager | 52 | weeks | 950 | 49400
Finishing Foreman / Assistant Site Manager | 52 | weeks | 500 | 26000
Labourer (including at handover) | 52 | weeks | 200 | 10400
Quantity Surveying /Commercial Management | 52 | weeks | 200 | 10400
Planner | 52 | weeks | 0 | 0
Health & Safety Officer | 52 | weeks | 0 | 0 | Included in Health and Safety Site Visits
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 1800 | 1800
Site office (inc furniture) | 52 | weeks | 37.35 | 1942.2
Meeting room (inc furniture) | 52 | weeks | 37.35 | 1942.2
Canteens and Kitchens | 52 | weeks | 36.75 | 1911
Drying room | 52 | weeks | 36.75 | 1911
Toilets and washrooms | 52 | weeks | 91 | 4732
Secure stores | 52 | weeks | 15 | 780
Telephones and Photocopiers (connection and charges) | 52 | weeks | 5 | 260
IT systems with email and internet capability | 52 | weeks | 10 | 520
Consumables and services associated with site accommodation | 52 | weeks | 50 | 2600
Fire points and fire fighting equipment | 1 | Item | 1400 | 1400
Main Contractor's Signboard | 1 | Item | 480 | 480
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 997.5 | 997.5
Cleaning
Site cleaning | 52 | weeks | 80 | 4160
Site set up
Tarmac and hardcored compound area | 1 | item | 0 | 0 | Compound constructed as permanent finish, therefore no additional cost
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item | 1400 | 1400
Temproary fencing to compound area | 1 | item | 600 | 600
Temporary security fencing to site perimeter | 1 | item | 4000 | 4000
Removal of compound on completion; reinstatement | 1 | item | 0 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks | 55 | 2860
Gas Supply | 52 | weeks | 15 | 780
Electric supply, Lighting and power | 52 | weeks | 125 | 6500
Drainage | 52 | weeks | 25 | 1300
Security
Night watchman | 52 | weeks | 1305 | 67860 | 75% of Programme
Pedestrian gates | 1 | item | 120 | 120
Vehicular gates | 1 | item | 240 | 240
CCTV cameras set up costs | 1 | item | 200 | 200
CCTV weekly charge | 52 | weeks | 175 | 9100
Material distribution
Forklift and driver | 26 | weeks | 1000 | 26000
Site plant
Small Dumper | 26 | weeks | 0 | 0 | Included in Groundworks rates
Mixer | 26 | weeks | 0 | 0 | Included in Small Tools and Equipment Sum
Road Sweeper including driver and fuel | 26 | weeks | 90 | 2340 | Allow 1nr per week (as an average)
Excavator / mini digger including driver and fuel | 26 | weeks | 0 | 0 | Included in Groundworks rates
Small tools and equiptment | 26 | weeks | 300 | 7800
Health and Safety
1st aid kit | 1 | item | 49.99 | 49.99
Health and safety site visits | 1 | item | 3200 | 3200
Falling from heights | 1 | item | 0 | 0 | Included in Relevant Packages
Scaffolding
External scaffolding including mat | 1 | item | 96618 | 96618
Adaption of Scaffolding | 1 | item | 0 | 0 | Included above
Internal Scaffolding | 1 | item | 0 | 0 | Included above
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 3000 | 3000
CDM regulations and health and safety plan | 1 | item | 500 | 500
Considerate constructors scheme | 1 | item | 300 | 300
SAP calculations and energy performance certificates | 1 | item | 1215 | 1215
Robust details | 1 | item | 1012.5 | 1012.5
Building Control Fees | 1 | item | 7582.8 | 7582.8
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 10000 | 10000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 98683.92 | 98683.92 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0
Concrete testing and reports | 1 | item | 832 | 832
Dilapidation Surveys | 1 | Item | 450 | 450
Sound testing | 1 | item | 0 | 0 | Robust Details Included
Air pressure tests | 1 | item | 900 | 900
Handover costs
Snagging costs | 1 | item | 0 | 0
Contract cleaners | 1 | item | 5940 | 5940
Clean to external areas | 1 | item | 500 | 500
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item | 0 | 0 | Included above
Resident handover packs | 27 | no | 5 | 135
Insurances and Guarantees
Project specific Insurance | 1 | Item | 8000 | 8000
6.5.1 Insurance | 1 | Item | 0 | 0 | Included in Overheads
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no | 200 | 5400
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | Covered by retention
Landscaped areas | 1 | item | 0 | 0 | Covered by retention
Total of preliminaries |  |  |  | 522455.11
Total of preliminaries expressed as a weekly cost |  |  |  | 10047.2137
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4.5%
Profit (expressed as a %) |  |  |  | 5.5%
Overheads and Profit Total |  |  |  | 10%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 206.41 | 14778.956 | 3 | 44336.868
Superstructures
Superstructures | 71.6 | m2 | 914.11 | 65450.276 | 3 | 196350.828
Allowance for Part L June 22 uplift | 1 | item | 3967.79 | 3967.79 | 3 | 11903.37
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 252591.066
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 219.93 | 15746.988 | 5 | 78734.94
Superstructures
Superstructures | 71.6 | m2 | 1009.07 | 72249.412 | 5 | 361247.06
Allowance for Part L June 22 uplift | 1 | item | 3931.22 | 3931.22 | 5 | 19656.1
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 459638.1
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 207.88 | 17711.376 | 10 | 177113.76
Superstructures
Superstructures | 85.2 | m2 | 932.23 | 79425.996 | 10 | 794259.96
Allowance for Part L June 22 uplift | 1 | item | 4106.76 | 4106.76 | 10 | 41067.6
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1012441.32
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 209.81 | 18064.641 | 3 | 54193.923
Superstructures
Superstructures | 86.1 | m2 | 922.55 | 79431.555 | 3 | 238294.665
Allowance for Part L June 22 uplift | 1 | item | 4106.76 | 4106.76 | 3 | 12320.28
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 304808.868
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 202.74 | 19098.108 | 6 | 114588.648
Superstructures
Superstructures | 94.2 | m2 | 881.85 | 83070.27 | 6 | 498421.62
Allowance for Part L June 22 uplift | 1 | item | 4194.52 | 4194.52 | 6 | 25167.12
Total cost for 3B5P houses (NDSS) | [5 empty] | 638177.388
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 10.72 | 85138.24
Preparatory Groundworks | 7942 | m² | 0.55 | 4368.1
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 107.47 | 87480.58
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 86.52 | 51219.84
Non Adopted footpath (tarmac) including all edgings | nil | m² | 0 | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 98.41 | 88569
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 77 | 94325
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 27.5 | 72572.5
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 203.5 | 5901.5
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 88 | 44616
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 92.4 | 37052.4
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 2200 | 59400
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 853143.16
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 522455.11
Substructure | [5 empty] | 468968.139
Superstructure | [5 empty] | 2088574.133
Part L Uplift | [5 empty] | 110114.47
External Works | [5 empty] | 853143.16
Post Contract Design Fees at say 3% | [5 empty] | 121297.6504
OHP | [5 empty] | 416455.2662
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4581007.9286
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4702006.6897
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4581007.9286
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 9283014.6183

## Low val Lot 4
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | McCaul Build Ltd
LOW VALUE LOT L4
TRADITIONAL CONSTRUCTION
LOCATION | North Yorkshire, West Yorkshire and East Yorkshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks | 0 | 0
Contracts Manager | 68 | weeks | 200 | 13600
Site Engineer | 68 | weeks | 200 | 13600
Site Manager | 68 | weeks | 950 | 64600
Finishing Foreman / Assistant Site Manager | 68 | weeks | 500 | 34000
Labourer (including at handover) | 68 | weeks | 200 | 13600
Quantity Surveying / Commercial Management | 68 | weeks | 200 | 13600
Planner | 68 | weeks | 0 | 0
Health & Safety Officer | 68 | weeks | 0 | 0 | Included in Health and Safety Site Visits
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 1800 | 1800
Site office (inc furniture) | 68 | weeks | 37.35 | 2539.8
Meeting room (inc furniture) | 68 | weeks | 37.35 | 2539.8
Canteens and Kitchens | 68 | weeks | 36.75 | 2499
Drying room | 68 | weeks | 36.75 | 2499
Toilets and washrooms | 68 | weeks | 91 | 6188
Secure stores | 68 | weeks | 15 | 1020
Telephones and Photocopiers (connection and charges) | 68 | weeks | 5 | 340
IT systems with email and internet capability | 68 | weeks | 10 | 680
Consumables and services associated with site accommodation | 68 | weeks | 50 | 3400
Fire points and fire fighting equipment | 1 | Item | 1400 | 1400
Main Contractor's Signboard | 1 | Item | 480 | 480
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 997.5 | 997.5
Cleaning
Site cleaning | 68 | weeks | 80 | 5440
Site set up
Tarmac and hardcore compound area | 1 | item | 0 | 0 | Compound constructed as permanent finish, therefore no additional cost
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item | 1400 | 1400
Temproary fencing to compound area | 1 | item | 600 | 600
Temporary security fencing to site perimeter | 1 | item | 4000 | 4000
Removal of compound on completion; reinstatement | 1 | item | 0 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks | 55 | 3740
Gas Supply | 68 | weeks | 15 | 1020
Electric supply, Lighting and power | 68 | weeks | 125 | 8500
Drainage | 68 | weeks | 25 | 1700
Security
Night watchman | 68 | weeks | 1305 | 88740 | 75% of Programme
Pedestrian gates | 1 | item | 120 | 120
Vehicular gates | 1 | item | 240 | 240
CCTV cameras set up costs | 1 | item | 200 | 200
CCTV weekly charge | 68 | weeks | 175 | 11900
Material distribution
Forklift and driver | 34 | weeks | 1000 | 34000
Site plant
Small Dumper | 34 | weeks | 0 | 0 | Included in Groundworks rates
Mixer | 34 | weeks | 0 | 0 | Included in Small Tools and Equipment Sum
Road Sweeper including driver and fuel | 34 | weeks | 90 | 3060 | Allow 1nr per week (as an average)
Excavator / mini digger including driver and fuel | 34 | weeks | 0 | 0 | Included in Groundworks rates
Small tools and equiptment | 34 | weeks | 300 | 10200
Health and Safety
1st aid kit | 1 | item | 49.99 | 49.99
Health and safety site visits | 1 | item | 4000 | 4000
Falling from heights | 1 | item | 0 | 0 | Included in Relevant Packages
Scaffolding
External scaffolding including mat | 1 | item | 78229 | 78229
Adaption of Scaffolding | 1 | item | 0 | 0 | Included above
Internal Scaffolding | 1 | item | 0 | 0 | Included above
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 3000 | 3000
CDM regulations and health and safety plan | 1 | item | 500 | 500
Considerate constructors scheme | 1 | item | 300 | 300
SAP calculations and energy performance certificates | 1 | item | 1215 | 1215
Robust details | 1 | item | 1012.5 | 1012.5
Building Control Fees | 1 | item | 7582.8 | 7582.8
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 10000 | 10000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 98683.92 | 98683.92 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0
Concrete testing and reports | 1 | item | 832 | 832
Dilapidation Surveys | 1 | Item | 450 | 450
Sound testing | 1 | item | 0 | 0 | Robust Details Included
Air pressure tests | 1 | item | 900 | 900
Handover costs
Snagging costs / inspections | 1 | item | 0 | 0
Contract cleaners | 1 | item | 5940 | 5940
Clean to external areas | 1 | item | 500 | 500
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item | 0 | 0 | Included above
Resident handover packs | 27 | no | 5 | 135
Insurances and Guarantees
Project specific Insurances | 1 | Item | 8000 | 8000
6.5.1 Insurance | 1 | Item | 0 | 0 | Included in Overheads
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no | 200 | 5400
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | Covered by retention
Landscaped areas | 1 | item | 0 | 0 | Covered by retention
Total of preliminaries |  |  |  | 585573.31
Total of preliminaries expressed as a weekly cost |  |  |  | 8611.3722
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4%
Profit (expressed as a %) |  |  |  | 4.5%
Overheads and Profit Total |  |  |  | 8.5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 206.41 | 14778.956 | 3 | 44336.868
Superstructures
Superstructures | 71.6 | m2 | 947.12 | 67813.792 | 3 | 203441.376
Allowance for Part L June 22 uplift | 1 | item | 3894.99 | 3894.99 | 3 | 11684.97
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 259463.214
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 219.93 | 15746.988 | 5 | 78734.94
Superstructures
Superstructures | 71.6 | m2 | 1016.44 | 72777.104 | 5 | 363885.52
Allowance for Part L June 22 uplift | 1 | item | 3859.09 | 3859.09 | 5 | 19295.45
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 461915.91
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 207.88 | 17711.376 | 10 | 177113.76
Superstructures
Superstructures | 85.2 | m2 | 928.12 | 79075.824 | 10 | 790758.24
Allowance for Part L June 22 uplift | 1 | item | 4031.4 | 4031.4 | 10 | 40314
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1008186
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 209.81 | 18064.641 | 3 | 54193.923
Superstructures
Superstructures | 86.1 | m2 | 915.02 | 78783.222 | 3 | 236349.666
Allowance for Part L June 22 uplift | 1 | item | 4031.4 | 4031.4 | 3 | 12094.2
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 302637.789
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 202.74 | 19098.108 | 6 | 114588.648
Superstructures
Superstructures | 94.2 | m2 | 882.33 | 83115.486 | 6 | 498692.916
Allowance for Part L June 22 uplift | 1 | item | 4117.56 | 4117.56 | 6 | 24705.36
Total cost for 3B5P houses (NDSS) | [5 empty] | 637986.924
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 10.72 | 85138.24
Preparatory Groundworks | 7942 | m² | 0.55 | 4368.1
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 107.47 | 87480.58
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 86.52 | 51219.84
Non Adopted footpath (tarmac) including all edgings | nil | m² | 0 | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 98.41 | 88569
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 77 | 94325
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 27.5 | 72572.5
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 203.5 | 5901.5
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 88 | 44616
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 92.4 | 37052.4
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 2200 | 59400
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 853143.16
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 585573.31
Substructure | [5 empty] | 468968.139
Superstructure | [5 empty] | 2093127.718
Part L Uplift | [5 empty] | 108093.98
External Works | [5 empty] | 853143.16
Post Contract Design Fees at say 3% | [5 empty] | 123267.1892
OH&P | [5 empty] | 359734.7472
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4591908.2434
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | McCaul Build Ltd
LOW VALUE LOT L4
TIMBER FRAME CONSTRUCTION
LOCATION | North Yorkshire, West Yorkshire and East Yorkshire
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks | 0 | 0
Contracts Manager | 52 | weeks | 200 | 10400
Site Engineer | 52 | weeks | 200 | 10400
Site Manager | 52 | weeks | 950 | 49400
Finishing Foreman / Assistant Site Manager | 52 | weeks | 500 | 26000
Labourer (including at handover) | 52 | weeks | 200 | 10400
Quantity Surveying /Commercial Management | 52 | weeks | 200 | 10400
Planner | 52 | weeks | 0 | 0
Health & Safety Officer | 52 | weeks | 0 | 0 | Included in Health and Safety Site Visits
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 1800 | 1800
Site office (inc furniture) | 52 | weeks | 37.35 | 1942.2
Meeting room (inc furniture) | 52 | weeks | 37.35 | 1942.2
Canteens and Kitchens | 52 | weeks | 36.75 | 1911
Drying room | 52 | weeks | 36.75 | 1911
Toilets and washrooms | 52 | weeks | 91 | 4732
Secure stores | 52 | weeks | 15 | 780
Telephones and Photocopiers (connection and charges) | 52 | weeks | 5 | 260
IT systems with email and internet capability | 52 | weeks | 10 | 520
Consumables and services associated with site accommodation | 52 | weeks | 50 | 2600
Fire points and fire fighting equipment | 1 | Item | 1400 | 1400
Main Contractor's Signboard | 1 | Item | 480 | 480
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 997.5 | 997.5
Cleaning
Site cleaning | 52 | weeks | 80 | 4160
Site set up
Tarmac and hardcored compound area | 1 | item | 0 | 0 | Compound constructed as permanent finish, therefore no additional cost
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item | 1400 | 1400
Temproary fencing to compound area | 1 | item | 600 | 600
Temporary security fencing to site perimeter | 1 | item | 4000 | 4000
Removal of compound on completion; reinstatement | 1 | item | 0 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks | 55 | 2860
Gas Supply | 52 | weeks | 15 | 780
Electric supply, Lighting and power | 52 | weeks | 125 | 6500
Drainage | 52 | weeks | 25 | 1300
Security
Night watchman | 52 | weeks | 1305 | 67860 | 75% of Programme
Pedestrian gates | 1 | item | 120 | 120
Vehicular gates | 1 | item | 240 | 240
CCTV cameras set up costs | 1 | item | 200 | 200
CCTV weekly charge | 52 | weeks | 175 | 9100
Material distribution
Forklift and driver | 26 | weeks | 1000 | 26000
Site plant
Small Dumper | 26 | weeks | 0 | 0 | Included in Groundworks rates
Mixer | 26 | weeks | 0 | 0 | Included in Small Tools and Equipment Sum
Road Sweeper including driver and fuel | 26 | weeks | 90 | 2340 | Allow 1nr per week (as an average)
Excavator / mini digger including driver and fuel | 26 | weeks | 0 | 0 | Included in Groundworks rates
Small tools and equiptment | 26 | weeks | 300 | 7800
Health and Safety
1st aid kit | 1 | item | 49.99 | 49.99
Health and safety site visits | 1 | item | 3200 | 3200
Falling from heights | 1 | item | 0 | 0 | Included in Relevant Packages
Scaffolding
External scaffolding including mat | 1 | item | 96618 | 96618
Adaption of Scaffolding | 1 | item | 0 | 0 | Included above
Internal Scaffolding | 1 | item | 0 | 0 | Included above
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 3000 | 3000
CDM regulations and health and safety plan | 1 | item | 500 | 500
Considerate constructors scheme | 1 | item | 300 | 300
SAP calculations and energy performance certificates | 1 | item | 1215 | 1215
Robust details | 1 | item | 1012.5 | 1012.5
Building Control Fees | 1 | item | 7582.8 | 7582.8
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 10000 | 10000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 98683.92 | 98683.92 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0
Concrete testing and reports | 1 | item | 832 | 832
Dilapidation Surveys | 1 | Item | 450 | 450
Sound testing | 1 | item | 0 | 0 | Robust Details Included
Air pressure tests | 1 | item | 900 | 900
Handover costs
Snagging costs | 1 | item | 0 | 0
Contract cleaners | 1 | item | 5940 | 5940
Clean to external areas | 1 | item | 500 | 500
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item | 0 | 0 | Included above
Resident handover packs | 27 | no | 5 | 135
Insurances and Guarantees
Project specific Insurance | 1 | Item | 8000 | 8000
6.5.1 Insurance | 1 | Item | 0 | 0 | Included in Overheads
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no | 200 | 5400
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | Covered by retention
Landscaped areas | 1 | item | 0 | 0 | Covered by retention
Total of preliminaries |  |  |  | 522455.11
Total of preliminaries expressed as a weekly cost |  |  |  | 10047.2137
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4%
Profit (expressed as a %) |  |  |  | 4.5%
Overheads and Profit Total |  |  |  | 8.5%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 206.41 | 14778.956 | 3 | 44336.868
Superstructures
Superstructures | 71.6 | m2 | 897.34 | 64249.544 | 3 | 192748.632
Allowance for Part L June 22 uplift | 1 | item | 3894.99 | 3894.99 | 3 | 11684.97
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 248770.47
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 219.93 | 15746.988 | 5 | 78734.94
Superstructures
Superstructures | 71.6 | m2 | 990.56 | 70924.096 | 5 | 354620.48
Allowance for Part L June 22 uplift | 1 | item | 3859.09 | 3859.09 | 5 | 19295.45
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 452650.87
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 207.88 | 17711.376 | 10 | 177113.76
Superstructures
Superstructures | 85.2 | m2 | 915.12 | 77968.224 | 10 | 779682.24
Allowance for Part L June 22 uplift | 1 | item | 4031.4 | 4031.4 | 10 | 40314
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 997110
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 209.81 | 18064.641 | 3 | 54193.923
Superstructures
Superstructures | 86.1 | m2 | 905.62 | 77973.882 | 3 | 233921.646
Allowance for Part L June 22 uplift | 1 | item | 4031.4 | 4031.4 | 3 | 12094.2
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 300209.769
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 202.74 | 19098.108 | 6 | 114588.648
Superstructures
Superstructures | 94.2 | m2 | 865.67 | 81546.114 | 6 | 489276.684
Allowance for Part L June 22 uplift | 1 | item | 4117.56 | 4117.56 | 6 | 24705.36
Total cost for 3B5P houses (NDSS) | [5 empty] | 628570.692
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 10.72 | 85138.24
Preparatory Groundworks | 7942 | m² | 0.55 | 4368.1
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 107.47 | 87480.58
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 86.52 | 51219.84
Non Adopted footpath (tarmac) including all edgings | nil | m² | 0 | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 98.41 | 88569
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 77 | 94325
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 27.5 | 72572.5
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 203.5 | 5901.5
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 88 | 44616
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 92.4 | 37052.4
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 2200 | 59400
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 853143.16
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 522455.11
Substructure | [5 empty] | 468968.139
Superstructure | [5 empty] | 2050249.682
Part L Uplift | [5 empty] | 108093.98
External Works | [5 empty] | 853143.16
Post Contract Design Fees at say 3% | [5 empty] | 120087.3021
OHP | [5 empty] | 350454.7767
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4473452.1498
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4591908.2434
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4473452.1498
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 9065360.3932

## Low val Lot 5
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | McCaul Build Ltd
LOW VALUE LOT L5
TRADITIONAL CONSTRUCTION
LOCATION | South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 68 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 68 | weeks | 0 | 0
Contracts Manager | 68 | weeks | 200 | 13600
Site Engineer | 68 | weeks | 200 | 13600
Site Manager | 68 | weeks | 950 | 64600
Finishing Foreman / Assistant Site Manager | 68 | weeks | 500 | 34000
Labourer (including at handover) | 68 | weeks | 200 | 13600
Quantity Surveying / Commercial Management | 68 | weeks | 200 | 13600
Planner | 68 | weeks | 0 | 0
Health & Safety Officer | 68 | weeks | 0 | 0 | Included in Health and Safety Site Visits
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 1800 | 1800
Site office (inc furniture) | 68 | weeks | 37.35 | 2539.8
Meeting room (inc furniture) | 68 | weeks | 37.35 | 2539.8
Canteens and Kitchens | 68 | weeks | 36.75 | 2499
Drying room | 68 | weeks | 36.75 | 2499
Toilets and washrooms | 68 | weeks | 91 | 6188
Secure stores | 68 | weeks | 15 | 1020
Telephones and Photocopiers (connection and charges) | 68 | weeks | 5 | 340
IT systems with email and internet capability | 68 | weeks | 10 | 680
Consumables and services associated with site accommodation | 68 | weeks | 50 | 3400
Fire points and fire fighting equipment | 1 | Item | 1400 | 1400
Main Contractor's Signboard | 1 | Item | 480 | 480
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 997.5 | 997.5
Cleaning
Site cleaning | 68 | weeks | 80 | 5440
Site set up
Tarmac and hardcore compound area | 1 | item | 0 | 0 | Compound constructed as permanent finish, therefore no additional cost
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item | 1400 | 1400
Temproary fencing to compound area | 1 | item | 600 | 600
Temporary security fencing to site perimeter | 1 | item | 4000 | 4000
Removal of compound on completion; reinstatement | 1 | item | 0 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 68 | weeks | 55 | 3740
Gas Supply | 68 | weeks | 15 | 1020
Electric supply, Lighting and power | 68 | weeks | 125 | 8500
Drainage | 68 | weeks | 25 | 1700
Security
Night watchman | 68 | weeks | 1305 | 88740 | 75% of Programme
Pedestrian gates | 1 | item | 120 | 120
Vehicular gates | 1 | item | 240 | 240
CCTV cameras set up costs | 1 | item | 200 | 200
CCTV weekly charge | 68 | weeks | 175 | 11900
Material distribution
Forklift and driver | 34 | weeks | 1000 | 34000
Site plant
Small Dumper | 34 | weeks | 0 | 0 | Included in Groundworks rates
Mixer | 34 | weeks | 0 | 0 | Included in Small Tools and Equipment Sum
Road Sweeper including driver and fuel | 34 | weeks | 90 | 3060 | Allow 1nr per week (as an average)
Excavator / mini digger including driver and fuel | 34 | weeks | 0 | 0 | Included in Groundworks rates
Small tools and equiptment | 34 | weeks | 300 | 10200
Health and Safety
1st aid kit | 1 | item | 49.99 | 49.99
Health and safety site visits | 1 | item | 4000 | 4000
Falling from heights | 1 | item | 0 | 0 | Included in Relevant Packages
Scaffolding
External scaffolding including mat | 1 | item | 78229 | 78229
Adaption of Scaffolding | 1 | item | 0 | 0 | Included above
Internal Scaffolding | 1 | item | 0 | 0 | Included above
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 3000 | 3000
CDM regulations and health and safety plan | 1 | item | 500 | 500
Considerate constructors scheme | 1 | item | 300 | 300
SAP calculations and energy performance certificates | 1 | item | 1215 | 1215
Robust details | 1 | item | 1012.5 | 1012.5
Building Control Fees | 1 | item | 7582.8 | 7582.8
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 10000 | 10000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 98683.92 | 98683.92 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0
Concrete testing and reports | 1 | item | 832 | 832
Dilapidation Surveys | 1 | Item | 450 | 450
Sound testing | 1 | item | 0 | 0 | Robust Details Included
Air pressure tests | 1 | item | 900 | 900
Handover costs
Snagging costs / inspections | 1 | item | 0 | 0
Contract cleaners | 1 | item | 5940 | 5940
Clean to external areas | 1 | item | 500 | 500
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item | 0 | 0 | Included above
Resident handover packs | 27 | no | 5 | 135
Insurances and Guarantees
Project specific Insurances | 1 | Item | 8000 | 8000
6.5.1 Insurance | 1 | Item | 0 | 0 | Included in Overheads
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 27 | no | 200 | 5400
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | Covered by retention
Landscaped areas | 1 | item | 0 | 0 | Covered by retention
Total of preliminaries |  |  |  | 585573.31
Total of preliminaries expressed as a weekly cost |  |  |  | 8611.3722
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4.5%
Profit (expressed as a %) |  |  |  | 5.5%
Overheads and Profit Total |  |  |  | 10%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 206.41 | 14778.956 | 3 | 44336.868
Superstructures
Superstructures | 71.6 | m2 | 955.97 | 68447.452 | 3 | 205342.356
Allowance for Part L June 22 uplift | 1 | item | 3931.39 | 3931.39 | 3 | 11794.17
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 261473.394
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 219.93 | 15746.988 | 5 | 78734.94
Superstructures
Superstructures | 71.6 | m2 | 1025.94 | 73457.304 | 5 | 367286.52
Allowance for Part L June 22 uplift | 1 | item | 3895.16 | 3895.16 | 5 | 19475.8
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 465497.26
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 207.88 | 17711.376 | 10 | 177113.76
Superstructures
Superstructures | 85.2 | m2 | 936.8 | 79815.36 | 10 | 798153.6
Allowance for Part L June 22 uplift | 1 | item | 4069.08 | 4069.08 | 10 | 40690.8
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1015958.16
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 209.81 | 18064.641 | 3 | 54193.923
Superstructures
Superstructures | 86.1 | m2 | 923.57 | 79519.377 | 3 | 238558.131
Allowance for Part L June 22 uplift | 1 | item | 4069.08 | 4069.08 | 3 | 12207.24
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 304959.294
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 202.74 | 19098.108 | 6 | 114588.648
Superstructures
Superstructures | 94.2 | m2 | 890.57 | 83891.694 | 6 | 503350.164
Allowance for Part L June 22 uplift | 1 | item | 4156.04 | 4156.04 | 6 | 24936.24
Total cost for 3B5P houses (NDSS) | [5 empty] | 642875.052
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 10.72 | 85138.24
Preparatory Groundworks | 7942 | m² | 0.55 | 4368.1
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 107.47 | 87480.58
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 86.52 | 51219.84
Non Adopted footpath (tarmac) including all edgings | nil | m² | 0 | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 98.41 | 88569
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 77 | 94325
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 27.5 | 72572.5
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 203.5 | 5901.5
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 88 | 44616
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 92.4 | 37052.4
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 2200 | 59400
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 853143.16
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 585573.31
Substructure | [5 empty] | 468968.139
Superstructure | [5 empty] | 2112690.771
Part L Uplift | [5 empty] | 109104.25
External Works | [5 empty] | 853143.16
Post Contract Design Fees at say 3% | [5 empty] | 123884.3889
OH&P | [5 empty] | 425336.4019
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4678700.4208
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | McCaul Build Ltd
LOW VALUE LOT L5
TIMBER FRAME CONSTRUCTION
LOCATION | South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 27 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 8 | 572.8 | NDSS
| 85.2 | 3B4P House |  | 10 | 852 | NDSS
| 86.1 | 3B4P House (side) |  | 3 | 258.3 | NDSS
| 94.2 | 3B5P House |  | 6 | 565.2 | NDSS
GIFA (m2) | 2248.3
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 52 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 52 | weeks | 0 | 0
Contracts Manager | 52 | weeks | 200 | 10400
Site Engineer | 52 | weeks | 200 | 10400
Site Manager | 52 | weeks | 950 | 49400
Finishing Foreman / Assistant Site Manager | 52 | weeks | 500 | 26000
Labourer (including at handover) | 52 | weeks | 200 | 10400
Quantity Surveying /Commercial Management | 52 | weeks | 200 | 10400
Planner | 52 | weeks | 0 | 0
Health & Safety Officer | 52 | weeks | 0 | 0 | Included in Health and Safety Site Visits
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item | 1800 | 1800
Site office (inc furniture) | 52 | weeks | 37.35 | 1942.2
Meeting room (inc furniture) | 52 | weeks | 37.35 | 1942.2
Canteens and Kitchens | 52 | weeks | 36.75 | 1911
Drying room | 52 | weeks | 36.75 | 1911
Toilets and washrooms | 52 | weeks | 91 | 4732
Secure stores | 52 | weeks | 15 | 780
Telephones and Photocopiers (connection and charges) | 52 | weeks | 5 | 260
IT systems with email and internet capability | 52 | weeks | 10 | 520
Consumables and services associated with site accommodation | 52 | weeks | 50 | 2600
Fire points and fire fighting equipment | 1 | Item | 1400 | 1400
Main Contractor's Signboard | 1 | Item | 480 | 480
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item | 997.5 | 997.5
Cleaning
Site cleaning | 52 | weeks | 80 | 4160
Site set up
Tarmac and hardcored compound area | 1 | item | 0 | 0 | Compound constructed as permanent finish, therefore no additional cost
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item | 1400 | 1400
Temproary fencing to compound area | 1 | item | 600 | 600
Temporary security fencing to site perimeter | 1 | item | 4000 | 4000
Removal of compound on completion; reinstatement | 1 | item | 0 | 0
Temp Services incl all connections, disconnections and usage
Water supply | 52 | weeks | 55 | 2860
Gas Supply | 52 | weeks | 15 | 780
Electric supply, Lighting and power | 52 | weeks | 125 | 6500
Drainage | 52 | weeks | 25 | 1300
Security
Night watchman | 52 | weeks | 1305 | 67860 | 75% of Programme
Pedestrian gates | 1 | item | 120 | 120
Vehicular gates | 1 | item | 240 | 240
CCTV cameras set up costs | 1 | item | 200 | 200
CCTV weekly charge | 52 | weeks | 175 | 9100
Material distribution
Forklift and driver | 26 | weeks | 1000 | 26000
Site plant
Small Dumper | 26 | weeks | 0 | 0 | Included in Groundworks rates
Mixer | 26 | weeks | 0 | 0 | Included in Small Tools and Equipment Sum
Road Sweeper including driver and fuel | 26 | weeks | 90 | 2340 | Allow 1nr per week (as an average)
Excavator / mini digger including driver and fuel | 26 | weeks | 0 | 0 | Included in Groundworks rates
Small tools and equiptment | 26 | weeks | 300 | 7800
Health and Safety
1st aid kit | 1 | item | 49.99 | 49.99
Health and safety site visits | 1 | item | 3200 | 3200
Falling from heights | 1 | item | 0 | 0 | Included in Relevant Packages
Scaffolding
External scaffolding including mat | 1 | item | 96618 | 96618
Adaption of Scaffolding | 1 | item | 0 | 0 | Included above
Internal Scaffolding | 1 | item | 0 | 0 | Included above
Fees and charges
Specialist site survey and level survey | 1 | item | 1500 | 1500
As built drawings and manuals | 1 | item | 3000 | 3000
CDM regulations and health and safety plan | 1 | item | 500 | 500
Considerate constructors scheme | 1 | item | 300 | 300
SAP calculations and energy performance certificates | 1 | item | 1215 | 1215
Robust details | 1 | item | 1012.5 | 1012.5
Building Control Fees | 1 | item | 7582.8 | 7582.8
Planning Condition Discharge Fees | 15 | no | 100 | 1500 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item | 10000 | 10000 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item | 98683.92 | 98683.92 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item | 0 | 0
Concrete testing and reports | 1 | item | 832 | 832
Dilapidation Surveys | 1 | Item | 450 | 450
Sound testing | 1 | item | 0 | 0 | Robust Details Included
Air pressure tests | 1 | item | 900 | 900
Handover costs
Snagging costs | 1 | item | 0 | 0
Contract cleaners | 1 | item | 5940 | 5940
Clean to external areas | 1 | item | 500 | 500
Skips | 8 | no | 200 | 1600
Lorry and tipping charges | 1 | item | 0 | 0 | Included above
Resident handover packs | 27 | no | 5 | 135
Insurances and Guarantees
Project specific Insurance | 1 | Item | 8000 | 8000
6.5.1 Insurance | 1 | Item | 0 | 0 | Included in Overheads
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 27 | no | 200 | 5400
External areas - paths, paving and adopted areas | 1 | item | 0 | 0 | Covered by retention
Landscaped areas | 1 | item | 0 | 0 | Covered by retention
Total of preliminaries |  |  |  | 522455.11
Total of preliminaries expressed as a weekly cost |  |  |  | 10047.2137
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 4.5%
Profit (expressed as a %) |  |  |  | 5.5%
Overheads and Profit Total |  |  |  | 10%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 206.41 | 14778.956 | 3 | 44336.868
Superstructures
Superstructures | 71.6 | m2 | 905.73 | 64850.268 | 3 | 194550.804
Allowance for Part L June 22 uplift | 1 | item | 3931.39 | 3931.39 | 3 | 11794.17
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 250681.842
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 | 219.93 | 15746.988 | 5 | 78734.94
Superstructures
Superstructures | 71.6 | m2 | 999.82 | 71587.112 | 5 | 357935.56
Allowance for Part L June 22 uplift | 1 | item | 3895.16 | 3895.16 | 5 | 19475.8
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 456146.3
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 | 207.88 | 17711.376 | 10 | 177113.76
Superstructures
Superstructures | 85.2 | m2 | 923.68 | 78697.536 | 10 | 786975.36
Allowance for Part L June 22 uplift | 1 | item | 4069.08 | 4069.08 | 10 | 40690.8
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 1004779.92
3 bed 4 person House (constructed as a semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 | 209.81 | 18064.641 | 3 | 54193.923
Superstructures
Superstructures | 86.1 | m2 | 922.55 | 79431.555 | 3 | 238294.665
Allowance for Part L June 22 uplift | 1 | item | 4069.08 | 4069.08 | 3 | 12207.24
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 304695.828
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 | 202.74 | 19098.108 | 6 | 114588.648
Superstructures
Superstructures | 94.2 | m2 | 873.76 | 82308.192 | 6 | 493849.152
Allowance for Part L June 22 uplift | 1 | item | 4156.04 | 4156.04 | 6 | 24936.24
Total cost for 3B5P houses (NDSS) | [5 empty] | 633374.04
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 7942 | m² | 10.72 | 85138.24
Preparatory Groundworks | 7942 | m² | 0.55 | 4368.1
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 814 | m² | 107.47 | 87480.58
Adopted footpath 2m wide (tarmac) including all edgings | 592 | m² | 86.52 | 51219.84
Non Adopted footpath (tarmac) including all edgings | nil | m² | 0 | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 900 | m² | 98.41 | 88569
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 1225 | m² | 77 | 94325
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 2639 | m² | 27.5 | 72572.5
External low level Planting including topsoil and mulch | 660 | m² | 40 | 26400 | PROV SUM
Tree species (PC sum £300) | 67 | no | 300 | 20100 | PROV SUM
Plot timber gates | 29 | no | 203.5 | 5901.5
1800mm high close boarded timber fencing, concrete gravel boards and post | 507 | lm | 88 | 44616
2100mm high close boarded timber fencing, concrete gravel boards and post | 401 | lm | 92.4 | 37052.4
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 81000 | 81000 | PROV SUM
Plot drainage | 27 | item | 2200 | 59400
Land Drainage | 1 | item | 6000 | 6000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Electricity Mains Supply | 1 | item | 17250 | 17250 | PROV SUM
Gas Mains Supply | 1 | item | 23000 | 23000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 8250 | 8250 | PROV SUM
External Street Lighting Systems | 1 | item | 11500 | 11500 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 6000 | 6000 | PROV SUM
Total cost for External Works | [5 empty] | 853143.16
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 522455.11
Substructure | [5 empty] | 468968.139
Superstructure | [5 empty] | 2071605.541
Part L Uplift | [5 empty] | 109104.25
External Works | [5 empty] | 853143.16
Post Contract Design Fees at say 3% | [5 empty] | 120758.286
OHP | [5 empty] | 414603.4486
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4560637.9346
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 4678700.4208
TOTAL GREENFIELD SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 4560637.9346
TOTAL COMBINED SITE COST FOR 27 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 27 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 9239338.3554

## High val Lot 1
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
HIGH VALUE LOT H1 WEST
TRADITIONAL CONSTRUCTION
LOCATION | Greater Manchester, Merseyside, Cheshire, Derbyshire West, Staffordshire, Lancashire, Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 104 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 104 | weeks |  | 0
Contracts Manager | 104 | weeks |  | 0
Site Engineer | 104 | weeks |  | 0
Site Manager | 104 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 104 | weeks |  | 0
Labourer (including at handover) | 104 | weeks |  | 0
Quantity Surveying / Commercial Management | 104 | weeks |  | 0
Planner | 104 | weeks |  | 0
Health & Safety Officer | 104 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 104 | weeks |  | 0
Meeting room (inc furniture) | 104 | weeks |  | 0
Canteens and Kitchens | 104 | weeks |  | 0
Drying room | 104 | weeks |  | 0
Toilets and washrooms | 104 | weeks |  | 0
Secure stores | 104 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 104 | weeks |  | 0
IT systems with email and internet capability | 104 | weeks |  | 0
Consumables and services associated with site accommodation | 104 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 104 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 104 | weeks |  | 0
Gas Supply | 104 | weeks |  | 0
Electric supply, Lighting and power | 104 | weeks |  | 0
Drainage | 104 | weeks |  | 0
Security
Night watchman | 104 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 104 | weeks |  | 0
Material distribution
Forklift and driver | 52 | weeks |  | 0
Site plant
Small Dumper | 52 | weeks |  | 0
Mixer | 52 | weeks |  | 0
Road Sweeper including driver and fuel | 52 | weeks |  | 0
Excavator / mini digger including driver and fuel | 52 | weeks |  | 0
Small tools and equiptment | 52 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 15 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 80 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 80 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 16 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 16 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 16 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 7 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 7 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 7 | 0
Total cost for 3B4P mid mews houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 22 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 22 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 22 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 108.3 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² |  | 0
Preparatory Groundworks | 19182 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | 125 | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² |  | 0
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item |  | 0
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 728300
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 728300
Post Contract Design Fees at say 3% | [5 empty] | 21849
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 750149
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
HIGH VALUE LOT H1 WEST
TIMBER FRAME CONSTRUCTION
LOCATION | Greater Manchester, Merseyside, Cheshire, Derbyshire West, Staffordshire, Lancashire, Cumbria
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 86 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 86 | weeks |  | 0
Contracts Manager | 86 | weeks |  | 0
Site Engineer | 86 | weeks |  | 0
Site Manager | 86 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 86 | weeks |  | 0
Labourer (including at handover) | 86 | weeks |  | 0
Quantity Surveying /Commercial Management | 86 | weeks |  | 0
Planner | 86 | weeks |  | 0
Health & Safety Officer | 86 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 86 | weeks |  | 0
Meeting room (inc furniture) | 86 | weeks |  | 0
Canteens and Kitchens | 86 | weeks |  | 0
Drying room | 86 | weeks |  | 0
Toilets and washrooms | 86 | weeks |  | 0
Secure stores | 86 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 86 | weeks |  | 0
IT systems with email and internet capability | 86 | weeks |  | 0
Consumables and services associated with site accommodation | 86 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 86 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 86 | weeks |  | 0
Gas Supply | 86 | weeks |  | 0
Electric supply, Lighting and power | 86 | weeks |  | 0
Drainage | 86 | weeks |  | 0
Security
Night watchman | 86 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 86 | weeks |  | 0
Material distribution
Forklift and driver | 43 | weeks |  | 0
Site plant
Small Dumper | 43 | weeks |  | 0
Mixer | 43 | weeks |  | 0
Road Sweeper including driver and fuel | 43 | weeks |  | 0
Excavator / mini digger including driver and fuel | 43 | weeks |  | 0
Small tools and equiptment | 43 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 1 | item |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 15 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 80 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 80 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %)
Profit (expressed as a %)
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 16 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 16 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 16 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 7 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 7 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 7 | 0
Total cost for 3B4P mid mews houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 22 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 22 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 22 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 108.3 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² |  | 0
Preparatory Groundworks | 19182 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | 125 | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² |  | 0
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item |  | 0
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 728300
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 728300
Post Contract Design Fees at say 3% | [5 empty] | 21849
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 750149
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 750149
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 750149
TOTAL COMBINED SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 80 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 1500298

## High val Lot 2
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
HIGH VALUE LOT H2 EAST
TRADITIONAL CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham, North Yorkshire, West Yorkshire, East Yorkshire, South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main adopted road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 104 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT Design and Build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on traditional masonry construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 104 | weeks |  | 0
Contracts Manager | 104 | weeks |  | 0
Site Engineer | 104 | weeks |  | 0
Site Manager | 104 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 104 | weeks |  | 0
Labourer (including at handover) | 104 | weeks |  | 0
Quantity Surveying / Commercial Management | 104 | weeks |  | 0
Planner | 104 | weeks |  | 0
Health & Safety Officer | 104 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 104 | weeks |  | 0
Meeting room (inc furniture) | 104 | weeks |  | 0
Canteens and Kitchens | 104 | weeks |  | 0
Drying room | 104 | weeks |  | 0
Toilets and washrooms | 104 | weeks |  | 0
Secure stores | 104 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 104 | weeks |  | 0
IT systems with email and internet capability | 104 | weeks |  | 0
Consumables and services associated with site accommodation | 104 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 104 | weeks |  | 0
Site set up
Tarmac and hardcore compound area | 1 | item |  | 0
Temporary roads incl demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 104 | weeks |  | 0
Gas Supply | 104 | weeks |  | 0
Electric supply, Lighting and power | 104 | weeks |  | 0
Drainage | 104 | weeks |  | 0
Security
Night watchman | 104 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 104 | weeks |  | 0
Material distribution
Forklift and driver | 52 | weeks |  | 0
Site plant
Small Dumper | 52 | weeks |  | 0
Mixer | 52 | weeks |  | 0
Road Sweeper including driver and fuel | 52 | weeks |  | 0
Excavator / mini digger including driver and fuel | 52 | weeks |  | 0
Small tools and equiptment | 52 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 15 | no |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs / inspections | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 15 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 80 | no |  | 0
Insurances and Guarantees
Project specific Insurances | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects / Maintenance to dwellings | 80 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 16 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 16 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 16 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 7 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 7 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 7 | 0
Total cost for 3B4P mid mews houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 22 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 22 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 22 | 0
Total cost for 3B5P houses (NDSS) | [5 empty] | 0
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 108.3 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² |  | 0
Preparatory Groundworks | 19182 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | 125 | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² |  | 0
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item |  | 0
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 728300
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 728300
Post Contract Design Fees at say 3% | [5 empty] | 21849
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 750149
INNOVATION CHAIN NORTH
Framework of New build Construction Contractors 2024
PRICING SCHEDULE
TENDERER'S NAME | [insert]
HIGH VALUE LOT H2 EAST
TIMBER FRAME CONSTRUCTION
LOCATION | Northumberland, Tyne & Wear, Durham, North Yorkshire, West Yorkshire, East Yorkshire, South Yorkshire, North Nottinghamshire, Lincolnshire, Derbyshire East
Virtual Project Scenario
Nature of project | New Build Affordable Rent Units |  |  | 80 no
Size (m2) and Mix (no) of units | 71.6 | 2B3P House |  | 19 | 1360.4 | NDSS
| 85.2 | 3B4P House |  | 18 | 1533.6 | NDSS
| 86.1 | 3B4P House (side) |  | 11 | 947.1 | NDSS
| 94.2 | 3B5P House |  | 22 | 2072.4 | NDSS
| 108.3 | 4B6P House |  | 10 | 1083 | NDSS
GIFA (m2) | 6996.5
Site Access | Good access direct from main road network
Vandalism risk | High risk - CCTV required with security guard nights and weekends
Length of Contract | 86 | working weeks
Base Date / Commencement Date | 31st January 2024
Form of Contract | JCT design and build 2016 with ICN Amendments
Pricing schedule notes and guidance
1. All rates submitted should be as outlined in the RICS NRM2 Preliminaries (Main Contract)
2. Accommodation and welfare provisions shall be in strict accordance with the CDM Regulations 2015
3. All rates submitted will be applied and used as a basis for the future negotiation of Fixed Price Contracts for all projects within the aforementioned LOT for the full duration of the Framework Agreement. Annual inflationary increases will be applied from the commencement date of the framework and shall be in accordance with BCIS Tender Price Indices or as evidenced to the satisfaction of the instructing client.
4. All items listed below may not be specifically required on every individual project within this LOT. For the purposes of the evaluation each individual item shall be priced or, if included within another item, annotated accordingly identifying which item it is included within. ICN reserves the right to reject any priced schedules submitted with a tender which includes only summary costs or totals which are not fully completed.
5. Should the tenderer deem that a member of the Site Staff and Supervision team will not be required full time on projects within this LOT then the weekly rate shall be adjusted accordingly not the number of weeks. Consideration should be given that the rates inserted will be fixed for future AMP agreements (only subject to inflationary increases as noted above)
6. None of the measured quantities or descriptions are to be altered, all tendering bids are to be based upon a fixed price schedule for consistency.
7. Preliminaries are to be based on the contract period stated above based on timber frame construction. Each item is to be priced based on the relevant contract period. The period stated are for time on site and exclude lead in periods for discharge of pre-start planning conditions. Any other pre-start time costs should be included in the preliminaries. Any items not priced will be deemed not to be required on projects of a similar nature within the afoementioned LOT value range for the duration of the Framework Agreement.
8. Tenderers should allow the percentage for profit and corporate overhead [contractors margin] and these are to include: Contractors profit on net costs. Contracting companies corporate operating overheads on net costs which include cost of premises, employment of non site based staff [with the exception of visiting contract surveyors and construction manager] including estimators, customer care teams, business development managers, buyers, planners, resource, scheduling and programmers, directors and heads of departments, accounts, legal, financing, property costs, administration, IT, human resources, telecoms, transport and vehicles, corporate charges. All contractors contributions to Group overheads [where applicable]
9. The tenderer is to assume Fabric First construction to meet current Building Regulations but is to allow for all Part L uplifts which have been prevalent since June 2022 on a separate line as indicated
10. The tenderer should note that non completion of one schedule will not be a compliant tender - both timber frame and traditional need to be completed
11. The tenderer shall complete the pricing schedule based upon the Affordable Rent specification and Standard House Type layouts (as included within the tender documentation) excluding all abnormal costs.
12. The tenderer shall allow for any cranage and associated works within the timber frame superstructures rate not the preliminaries schedule.
Preliminaries | Quantity | Unit | Rate | Total | Notes
Project specific management and Staff
Project Manager | 86 | weeks |  | 0
Contracts Manager | 86 | weeks |  | 0
Site Engineer | 86 | weeks |  | 0
Site Manager | 86 | weeks |  | 0
Finishing Foreman / Assistant Site Manager | 86 | weeks |  | 0
Labourer (including at handover) | 86 | weeks |  | 0
Quantity Surveying /Commercial Management | 86 | weeks |  | 0
Planner | 86 | weeks |  | 0
Health & Safety Officer | 86 | weeks |  | 0
Site establishment
Delivery of temp accomodation to site and removal on completion | 1 | Item |  | 0
Site office (inc furniture) | 86 | weeks |  | 0
Meeting room (inc furniture) | 86 | weeks |  | 0
Canteens and Kitchens | 86 | weeks |  | 0
Drying room | 86 | weeks |  | 0
Toilets and washrooms | 86 | weeks |  | 0
Secure stores | 86 | weeks |  | 0
Telephones and Photocopiers (connection and charges) | 86 | weeks |  | 0
IT systems with email and internet capability | 86 | weeks |  | 0
Consumables and services associated with site accommodation | 86 | weeks |  | 0
Fire points and fire fighting equipment | 1 | Item |  | 0
Main Contractor's Signboard | 1 | Item |  | 0
Client/Homes England signboard; production, installation and removal (as ER's) | 1 | Item |  | 0
Cleaning
Site cleaning | 86 | weeks |  | 0
Site set up
Tarmac and hardcored compound area | 1 | item |  | 0
Temporary roads including demarcation for safe pedestrian and vehicular routes | 1 | item |  | 0
Temproary fencing to compound area | 1 | item |  | 0
Temporary security fencing to site perimeter | 1 | item |  | 0
Removal of compound on completion; reinstatement | 1 | item |  | 0
Temp Services incl all connections, disconnections and usage
Water supply | 86 | weeks |  | 0
Gas Supply | 86 | weeks |  | 0
Electric supply, Lighting and power | 86 | weeks |  | 0
Drainage | 86 | weeks |  | 0
Security
Night watchman | 86 | weeks |  | 0
Pedestrian gates | 1 | item |  | 0
Vehicular gates | 1 | item |  | 0
CCTV cameras set up costs | 1 | item |  | 0
CCTV weekly charge | 86 | weeks |  | 0
Material distribution
Forklift and driver | 43 | weeks |  | 0
Site plant
Small Dumper | 43 | weeks |  | 0
Mixer | 43 | weeks |  | 0
Road Sweeper including driver and fuel | 43 | weeks |  | 0
Excavator / mini digger including driver and fuel | 43 | weeks |  | 0
Small tools and equiptment | 43 | weeks |  | 0
Health and Safety
1st aid kit | 1 | item |  | 0
Health and safety site visits | 1 | item |  | 0
Falling from heights | 1 | item |  | 0
Scaffolding
External scaffolding including mat | 1 | item |  | 0
Adaption of Scaffolding | 1 | item |  | 0
Internal Scaffolding | 1 | item |  | 0
Fees and charges
Specialist site survey and level survey | 1 | item |  | 0
As built drawings and manuals | 1 | item |  | 0
CDM regulations and health and safety plan | 1 | item |  | 0
Considerate constructors scheme | 1 | item |  | 0
SAP calculations and energy performance certificates | 1 | item |  | 0
Robust details | 1 | item |  | 0
Building Control Fees | 1 | item |  | 0
Planning Condition Discharge Fees | 1 | item |  | 0 | tenderer to assume there are 15 conditions requiring discharge
Adoption Agreements for Section 278, 104 and 38 Agreements | 1 | item |  | 0 | tenderer to assume road and sewers on virtual plan to be adopted
NHBC (or equivalent) 12 year structural warranty cover | 1 | item |  | 0 | tenderer not to include for insolvency cover
Testing and reports
Methane and radon testing and reports | 1 | item |  | 0
Concrete testing and reports | 1 | item |  | 0
Dilapidation Surveys | 1 | Item |  | 0
Sound testing | 1 | item |  | 0
Air pressure tests | 1 | item |  | 0
Handover costs
Snagging costs | 1 | item |  | 0
Contract cleaners | 1 | item |  | 0
Clean to external areas | 1 | item |  | 0
Skips | 15 | no |  | 0
Lorry and tipping charges | 1 | item |  | 0
Resident handover packs | 80 | no |  | 0
Insurances and Guarantees
Project specific Insurance | 1 | Item |  | 0
6.5.1 Insurance | 1 | Item |  | 0
Performance bond / parent company guarantee / insolvency cover |  |  |  | NIL | Contractor to indicate on Supplier Questionnaire
Maintenance period
Defects/Maintenance to dwelling | 80 | no |  | 0
External areas - paths, paving and adopted areas | 1 | item |  | 0
Landscaped areas | 1 | item |  | 0
Total of preliminaries |  |  |  | 0
Total of preliminaries expressed as a weekly cost |  |  |  | 0
Overheads and Profit
Corporate overheads (expressed as a %) |  |  |  | 0%
Profit (expressed as a %) |  |  |  | 0%
Overheads and Profit Total |  |  |  | 0%
Construction Costs
2 bed 3 person house (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 3 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 3 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 3 | 0
Total cost for 2B3P mid mews houses (NDSS) | [5 empty] | 0
2 bed 3 person house (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 71.6 | m2 |  | 0 | 16 | 0
Superstructures
Superstructures | 71.6 | m2 |  | 0 | 16 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 16 | 0
Total cost for 2B3P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a mid mews) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 7 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 7 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 7 | 0
Total cost for 3B4P mid mews houses (Non NDSS) | [5 empty] | 0
3 bed 4 person House (constructed as a semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 85.2 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 85.2 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 4 person house (constructed as semi detached) (side entrance) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 86.1 | m2 |  | 0 | 11 | 0
Superstructures
Superstructures | 86.1 | m2 |  | 0 | 11 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 11 | 0
Total cost for 3B4P semi detached houses (NDSS) | [5 empty] | 0
3 bed 5 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 94.2 | m2 |  | 0 | 22 | 0
Superstructures
Superstructures | 94.2 | m2 |  | 0 | 22 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 22 | 0
Total cost for 3B5P houses (Non NDSS) | [5 empty] | 0
4 bed 6 person house (constructed as semi detached) | Quantity | Unit | Rate | Total | No of units | Total
Substructures
Traditional strip foundation and lowest floor construction (expressed as GIFA) | 108.3 | m2 |  | 0 | 10 | 0
Superstructures
Superstructures | 108.3 | m2 |  | 0 | 10 | 0
Allowance for Part L June 22 uplift | 1 | item |  | 0 | 10 | 0
Total cost for 4B6P semi detached houses (NDSS) | [5 empty] | 0
EXTERNAL WORKS | Quantity | Unit | Rate | Total
Site Preparation Works
Site Clearance (assume 300mm deep inert to landfil) | 19182 | m² |  | 0
Preparatory Groundworks | 19182 | m² |  | 0
Roads, Paths, Pavings and Surfacings
Adopted Road (tarmac) including all kerbs and dropped kerbs | 1389 | m² |  | 0
Adopted footpath 2m wide (tarmac) including all edgings | 1022 | m² |  | 0
Non Adopted footpath (tarmac) including all edgings | 125 | m² |  | 0
Non Adopted Road and Parking Space (tarmac) including all edgings | 3467 | m² |  | 0
PCC concrete paving 600x600mm (PC sum £40/m2 supply) incl edgings | 2134 | m² |  | 0
Soft Landscaping, Planting and Irrigation Systems
Turf and topsoil (300mm deep) | 6065 | m² |  | 0
External low level Planting including topsoil and mulch | 1515 | m² | 40 | 60600 | PROV SUM
Tree species (PC sum £300) | 134 | no | 300 | 40200 | PROV SUM
Plot timber gates | 86 | no |  | 0
1800mm high close boarded timber fencing, concrete gravel boards and post | 1282 | lm |  | 0
2100mm high close boarded timber fencing, concrete gravel boards and post | 390 | lm |  | 0
External Drainage
Site wide Surface Water and Foul Water Drainage | 1 | item | 290000 | 290000 | PROV SUM
Plot drainage | 80 | item |  | 0
Land Drainage | 1 | item | 20000 | 20000 | PROV SUM
External Services
Water Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Electricity Mains Supply | 1 | item | 62500 | 62500 | PROV SUM
Gas Mains Supply | 1 | item | 82000 | 82000 | PROV SUM
Telecommunications and other Communication System Connections | 1 | item | 28500 | 28500 | PROV SUM
External Street Lighting Systems | 1 | item | 42000 | 42000 | PROV SUM
Builder's Work In Connection with External Services | 1 | item | 20500 | 20500 | PROV SUM
Total cost for External Works | [5 empty] | 728300
SUMMARY | [5 empty] | TOTAL COST
Preliminaries | [5 empty] | 0
Substructure | [5 empty] | 0
Superstructure | [5 empty] | 0
Part L Uplift | [5 empty] | 0
External Works | [5 empty] | 728300
Post Contract Design Fees at say 3% | [5 empty] | 21849
OH&P | [5 empty] | 0
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 750149
FINAL SUMMARY
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 750149
TOTAL GREENFIELD SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION | [5 empty] | 750149
TOTAL COMBINED SITE COST FOR 80 AFFORDABLE RENT UNITS IN TIMBER FRAME CONSTRUCTION AND 80 UNITS IN TRADITIONAL CONSTRUCTION | [5 empty] | 1500298