## KPI
ICN KPI Workbook - Employers Agent
Scheme name:
No. of units:
Client:
PC Date:
Newbuild/Refurb:
Contract Value:
Contractor:
Architect:
Employers Agent:
Development Project Manager:
| Neighbourhood Services Manager: |  |  | Please complete orange cells
| Scoring | Click on cell and select from drop down list | Score | Client comments to explain scoring:
Pre-Contract | Accuracy of final construction cost estimate v tender sum |  | #N/A
| Completion of Tender/VFM report in accordance with ICN template |  | #N/A
| Efficiently chair all monthly design team meetings |  | #N/A
| Timely issue of design team meeting minutes and enclosures |  | #N/A
| Issue of JCT contract documents by required deadline |  | #N/A
In Contract | Completion of monthly cost reports and cashflow as ICN template |  | #N/A
| Timely and correct issue of all contract instructions |  | #N/A
| Timely issue of site meeting minutes and enclosures |  | #N/A
| Accurate recording of information required for handover |  | #N/A
| Complete fortnightly progress visits to site |  | #N/A
| Efficiently chair all monthly site meetings |  | #N/A
| Accuracy of estimated programme and programme monitoring |  | #N/A
| Management of project risk register from inception to completion |  | #N/A
| Timely and accurate agreement and issue of the Final Account |  | #N/A
| Practice resourced scheme in line with project requirements |  | #N/A
Defects | Timely and accurate documentation throughout Defects Period |  | #N/A
|  | Client Satisfaction Average | #N/A
Accuracy of final construction cost estimate v tender sum
|  | 0-5% difference plus or minus, scores 5 | 5
|  | 5-10% difference plus or minus scores 3 | 3
|  | Over 10% difference plus or minus, scores 0 | 0
Completion of Tender/VFM report in accordance with GPHG template
|  | Report 100% as template, scores 5 | 5
|  | Report has minor omissions, scores 3 | 3
|  | Report has major omissions / does not comply, scores 0 | 0
Efficiently chair all monthly site meetings
|  | 100% attendance and efficiently chaired, scores 5 | 5
|  | <3 missed meetings with prior notice, scores 3 | 3
|  | Lack of commitment to attend and chair project meetings, scores 0 | 0
Timely issue of site meeting minutes and enclosures
|  | Issued within 7 working days on average, scores 5 | 5
|  | Issued within 7-10 working days on average, scores 3 | 3
|  | Issued later than 10 working days on average, scores 0 | 0
Timely issue of site meeting minutes and enclosures
|  | Issued within 7 working days on average, scores 5 | 5
|  | Issued within 7-10 working days on average, scores 3 | 3
|  | Issued later than 10 working days on average, scores 0 | 0
Issue of JCT contract documents by required deadline
|  | Meets deadline, scores 5 | 5
|  | Up to 1 week delay in issue, scores 3 | 3
|  | More than 1 week delay in issue, scores 0 | 0
Completion of monthly cost reports and cashflow as ICN templates
|  | Report format 100% as template, scores 5 | 5
|  | Reports have minor omissions, scores 3 | 3
|  | Reports has major omissions / do not comply, scores 0 | 0
Timely and correct issue of all JCT contract instructions
|  | All contract instructions issued on time, scores 5 | 5
|  | Minor delays or errors in issue, scores 3 | 3
|  | Instructions not issued correctly or delayed, scores 0 | 0
Timely issue of site meeting minutes and enclosures
|  | Issued within 7 working days on average, scores 5 | 5
|  | Issued within 7-10 working days on average, scores 3 | 3
|  | Issued later than 10 working days on average, scores 0 | 0
Accurate recording of information required for handover
|  | 100% information recorded as template, scores 5 | 5
|  | Minor omissions from template information, scores 3 | 3
|  | Major omissions from template information, scores 0 | 0
Complete fortnightly progress visits to site
|  | 100% fortnighly visits completed over contract duration, scores 5 | 5
|  | 75%-100% fortnighly visits completed over contract duration, scores 3 | 3
|  | <75% fortnighly visits completed over contract duration, scores 0 | 0
Efficiently chair all monthly site meetings
|  | 100% attendance and efficiently chaired, scores 5 | 5
|  | <3 missed meetings with prior notice, scores 3 | 3
|  | Lack of commitment to attend and chair project meetings, scores 0 | 0
Accuracy of estimated programme and programme monitoring
|  | Programme fully assessed; proactive reporting of all programme movement, scores 5 | 5
|  | Minor inaccuracies in programme monitoring and delay reporting, scores 3 | 3
|  | Failure to assess programme and accurate report on delays, scores 0 | 0
Management of project risk register from inception to completion
|  | Risk register prepared and updated every month, scores 5 | 5
|  | Risk register prepared but not updated fully on a monthly basis, scores 3 | 3
|  | No risk register prepared or no updating of register completed, scores 0 | 0
Timely and accurate agreement and issue of the Final Account
|  | Issued within 14 working days of PC, scores 5 | 5
|  | Issued within 14-28 working days of PC, scores 3 | 3
|  | Issued later than 28 working days of PC, scores 0 | 0
Practice resourced scheme in line with project requirements
|  | No resourcing concerns on the project and full support from the Employer's Agent, scores 5 | 5
|  | Positive response to any resourcing issues raised and adequate support from the Employer's Agent, scores 3 | 3
|  | Poor response to any resourcing issues raised and lack of support from the Employer's Agent, scores 0 | 0
Timely and accurate documentation throughout Defects Period
|  | Issued within 7 working days on average, scores 5 | 5
|  | Issued within 7-10 working days on average, scores 3 | 3
|  | Issued later than 10 working days on average, scores 0 | 0